## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08260 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line in Champali mouza within Champali w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000699/2021-2022 | 1987/HSD | 02/12/2021 | 09/12/2021 | S.K.ENTERPRISE. | 2.44 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08260 | Retrofitting | Acceptance cum work order for Protection of newly laid DI/UPVC pipe line by UC bullah pile at different places in Champali mouza within Champali w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000703/2021-2022 | 1991/HSD | 02/12/2021 | 12/12/2021 | M/S NIRMAN CONSTRUCTION. | 4.38 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08260 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in diff. mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Champali w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000339/2021-2022 | 1671/BD | 08/09/2021 | 23/10/2021 | M/S NIRMAN CONSTRUCTION. | 77.7 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08260 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 1810/BD | 19/06/2023 | 19/06/2023 | Resource Division | 13.49 | 0 | 0 | 0
Total | [13 empty] | 98.02 | 0 | 0