## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08262 | Retrofitting | Construction of Approach Road Head Work at site for Augmentation of Kurulia (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000731/2023-2024 | 621/Bon | 08/08/2023 | 02/09/2023 | GHOSH CONSTRUCTION. | 4.75 | 4.74 | 99.67 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08262 | Retrofitting | Construction of Approach Road at 2ndT/W site for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001065/2023-2024 | 558/Bon | 18/07/2023 | 02/08/2023 | ROY ENGINEERS. | 0.93 | 0.92 | 98.71 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08262 | Retrofitting | Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001049/2023-2024 | 643/Bon | 14/08/2023 | 04/09/2023 | M/S SAYAN ENTERPRISE. | 1.59 | 1.57 | 98.15 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08262 | Retrofitting | Improvement of Iron Elimination Plant and other related allied works at Kurulia (Zone - II) W/S Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000891/2023-2024 | 638/Bon | 14/08/2023 | 29/08/2023 | SAMBHU RAY CHOWDHURY. | 2.49 | 2.41 | 96.83 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08262 | Retrofitting | Formal work order for Improvement of Iron Elimination Plant and other related allied works at Kurulia (Zone-I) W/S Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000896/2023-2024 | 637/Bon | 14/08/2023 | 29/08/2023 | TAPAN GHOSH. | 2.45 | 0 | 0 | 99
Total | [13 empty] | 12.22 | 9.63 | 78.81