## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08263 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Helencha Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001334/2021-2022 | 134/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08263 | Retrofitting | Hiring of 1(one) no Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:-01/02/2023 to 31/07/2023). | Assistant Engineer | Junior Engineer | ORD/001341/2022-2023 | 99/Bon | 31/01/2023 | 31/07/2023 | ROY ENGINEERS. | 0.86 | 1.26 | 146.31 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08263 | Retrofitting | Repairing & Renovation of Head Work Pump House site and allied works at Helencha water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000624/2022-2023 | 409/Bon | 23/08/2022 | 04/09/2022 | KAMAL HALDAR. | 3 | 2.96 | 98.86 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08263 | Retrofitting | Hiring of 1(one) no Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:-01/02/2023 to 31/07/2023). | Assistant Engineer | Junior Engineer | ORD/001480/2022-2023 | 99/.BON | 31/01/2023 | 31/07/2023 | ROY ENGINEERS. | 0.86 | 0.65 | 75.99 | 100
Total | [13 empty] | 9.55 | 9.71 | 101.65