## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08264 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gangrapota Water Supply Scheme at Bongaon Block under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000643/2021-2022 | 2175/BD | 18/11/2021 | 16/02/2022 | AMIT KUMAR BOSE. | 167.22 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08264 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Gangrapota Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/001117/2021-2022 | 611/Bon | 31/12/2021 | 20/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.12 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08264 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Kamarpur & Adj. Mouzas W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000935/2021-2022 | 558/HAB | 20/12/2021 | 30/12/2021 | UMWELT ENGINEER PVT.LTD. | 3.42 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08264 | Retrofitting | Construction of Boundary wall at 2nd Pump House site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000643/2023-2024 | 614/Bon | 08/08/2023 | 29/08/2023 | A.D.ENTERPRISE. | 3.66 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08264 | Retrofitting | Construction of Approach Road Head Work at site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000636/2023-2024 | 619/BON | 08/08/2023 | 28/08/2023 | MA CONSTRUCTION. | 3.98 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08264 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000002/2021-2022 | 2238/BD | 24/11/2021 | 24/11/2021 | Resource Division | 10.26 | 0 | 0 | 0
Total | [13 empty] | 192.67 | 0 | 0