## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Krishnachandrapur Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08265 | Retrofitting | Hiring of 1(one) no Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:-01/02/2022 to 31/01/2023). | Assistant Engineer | Junior Engineer | ORD/001396/2021-2022 | 45/Bon | 31/01/2022 | 01/02/2022 | ROY ENGINEERS. | 1.73 | 1.68 | 97.1 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Krishnachandrapur Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08265 | Retrofitting | Construction of Boundary wall at 2nd T/W site for Augmentation of Krishnacandrapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000716/2023-2024 | 611/Bon | 08/08/2023 | 29/08/2023 | ACHINTA KUMAR HALDER. | 4.7 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Krishnachandrapur Piped Water Supply Scheme, Bongaon Block (Phase-I) | SM/08265 | Retrofitting | Construction of Approach Road at 2nd T/W site for Augmentation of Krishnachandrapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000969/2023-2024 | 557/Bon | 18/07/2023 | 02/08/2023 | ACHINTA KUMAR HALDER. | 0.91 | 0 | 0 | 0
Total | [13 empty] | 7.34 | 1.68 | 22.9