## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08267 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KONIARA Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001105/2021-2022 | 164/BD | 19/01/2022 | 18/02/2022 | ROY CHOWDHURY CONSTRUCTION. | 35.78 | 35.74 | 99.88 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08267 | Retrofitting | Acceptance cum work order for additional Survey Work For DPR Preparation of Sahebkhali (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000953/2021-2022 | 2147/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.84 | 2.79 | 98.33 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08267 | Retrofitting | Laying of distribution pipe line for smoothly water supply all over back site villagers and other allied works at Koniara water supply scheme under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2022-2023 | 404/Bon | 23/08/2022 | 07/09/2022 | ROY CHOWDHURY CONSTRUCTION. | 3.49 | 3.47 | 99.39 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) | SM/08267 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 2868/BD | 21/09/2022 | 21/09/2022 | Resource Division | 2.14 | 0 | 0 | 0
Total | [13 empty] | 44.24 | 41.99 | 94.92