## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chikanpara Piped Water Supply Scheme, Gaighata Block (Phase-I) | SM/08269 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Chikanpara Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001351/2021-2022 | 147/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.37 | 4.37 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chikanpara Piped Water Supply Scheme, Gaighata Block (Phase-I) | SM/08269 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of CHIKANPARA Water Supply Scheme at GAIGHATA Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001157/2021-2022 | 259/BD | 28/01/2022 | 28/04/2022 | SUPER SKILL. | 195.19 | 194.56 | 99.68 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chikanpara Piped Water Supply Scheme, Gaighata Block (Phase-I) | SM/08269 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000103/2022-2023 | 3658/BD | 13/12/2022 | 13/12/2022 | Resource Division | 15.09 | 0 | 0 | 0
Total | [13 empty] | 214.65 | 198.93 | 92.67