## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area DHOPABERIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08638 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Dhopaberia Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000337/2021-2022 | 1652/BD | 07/09/2021 | 07/10/2021 | UTPAL CONSTRUCTION & CO. | 53.77 | 52.68 | 97.96 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area DHOPABERIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08638 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for DHOPABERIA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001959/2021-2022 | 310/BHTSD | 07/03/2022 | 22/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.6 | 3.6 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area DHOPABERIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08638 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 2242/BD | 24/11/2021 | 24/11/2021 | Resource Division | 10.26 | 0 | 0 | 0
Total | [13 empty] | 67.63 | 56.27 | 83.21