## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Mirzanagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08639 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for MIRZANAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001956/2021-2022 | 307/BHTSD | 07/03/2022 | 22/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.78 | 3.69 | 97.6 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Mirzanagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08639 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Mirzanagar Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000335/2021-2022 | 1656/BD | 07/09/2021 | 22/10/2021 | CHANCHAL ENTERPRISE & CO. | 85.87 | 83.5 | 97.24 | 1
Total | [13 empty] | 89.66 | 87.19 | 97.25