## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis (for 6months from 01-01-2022 to 30-06-2022) for the Office of the Assistant Engineer (HQ), Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001167/2021-2022 | 2686/BD | 31/12/2021 | 30/06/2022 | M/S SAMIT CHANDRA DEY. | 0.86 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BITHARI ZONE -1 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002508/2021-2022 | 450 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BARA BANKRA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002519/2021-2022 | 441 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.57 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for NITYANANDAKATI BALTI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002520/2021-2022 | 440 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for MAMINPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001954/2021-2022 | 305/BHTSD | 07/03/2022 | 22/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.15 | 0 | 0 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for GOKULPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002512/2021-2022 | 448 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.32 | 0 | 0 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for TARANIPUR ZONE -1 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002514/2021-2022 | 446 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 0 | 0 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for DOBILA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002511/2021-2022 | 449 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.5 | 0 | 0 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for KAPILESWARPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002515/2021-2022 | 445 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 0 | 0 | 1
10 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Gobindapur Water Supply Scheme at Baduria Block, Dist- North 24 Parganas under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000822/2021-2022 | 2438/BD | 13/12/2021 | 13/03/2022 | UTPAL CONSTRUCTION & CO. | 224.17 | 0 | 0 | 1
11 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08641 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 2859/BD | 21/09/2022 | 21/09/2022 | Resource Division | 27.73 | 0 | 0 | 0
Total | [13 empty] | 284.64 | 0 | 0