## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08642 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Gotra Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I). | Assistant Engineer | Junior Engineer | ORD/000350/2021-2022 | 1676/BD | 08/09/2021 | 23/10/2021 | M/S NIRMAN CONSTRUCTION. | 86.18 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08642 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Talsa W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000938/2021-2022 | 559/HAB | 20/12/2021 | 30/12/2021 | UMWELT ENGINEER PVT.LTD. | 3.67 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08642 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Chhaimalpur Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000986/2021-2022 | 2169/HSD | 28/12/2021 | 18/01/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.79 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08642 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for GOTRA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001940/2021-2022 | 196/BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.3 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | SM/08642 | Retrofitting | Hiring Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period 01.07.2023 to 31.12.2023 for Six Month) | Assistant Engineer |  | ORD/000785/2023-2024 | 604/BHTSD | 28/06/2023 | 29/12/2023 | DEB KUMAR DAS. | 0.87 | 0 | 0 | 33
Total | [13 empty] | 97.81 | 0 | 0