## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) | SM/08644 | Retrofitting | Additional Survey work for DPR Preparation for BAJITPUR ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001982/2021-2022 | 354/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.63 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) | SM/08644 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BAJITPUR ZONE 1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001981/2021-2022 | 353/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) | SM/08644 | Retrofitting | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area under BAJITPUR ZONE-I Water Supply Scheme at Baduria Block, District- North 24 Parganas under Barasat Division,PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001082/2021-2022 | 141/BD | 18/01/2022 | 18/04/2022 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 266.04 | 0 | 0 | 1
Total | [13 empty] | 271.63 | 0 | 0