## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Zafarpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08645 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Zafarpur Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000831/2021-2022 | 2461/BD | 15/12/2021 | 29/01/2022 | SHIBU BISWAS. | 81.63 | 81.47 | 99.81 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Zafarpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08645 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for ZAFARPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001947/2021-2022 | 203/BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.3 | 4.19 | 97.41 | 1
Total | [13 empty] | 85.93 | 85.66 | 99.69