## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08647 | Retrofitting | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Gokna Water Supply Scheme at Baduria Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001166/2021-2022 | 315/BD | 01/02/2022 | 02/05/2022 | KINGS & CO. | 220.6 | 214.18 | 97.09 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08647 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for GOKNA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001988/2021-2022 | 360/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.96 | 4.96 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08647 | Retrofitting | Additional Survey work for DPR Preparation for GOKNA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001991/2021-2022 | 361/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.59 | 4.53 | 98.76 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08647 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 2986/BD | 29/09/2022 | 29/09/2022 | Resource Division | 0.06 | 0 | 0 | 0
Total | [13 empty] | 230.19 | 223.66 | 97.16