## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of NITYANANDAKATI BALTI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08651 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Nityanandakati Balti Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase I) | Assistant Engineer | Junior Engineer | ORD/000830/2021-2022 | 2460/BD | 15/12/2021 | 29/01/2022 | SHIBU BISWAS. | 66.16 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of NITYANANDAKATI BALTI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08651 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Durgamondop Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000994/2021-2022 | 2175/HSD | 28/12/2021 | 18/01/2022 | UMWELT ENGINEER PVT.LTD. | 4.15 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of NITYANANDAKATI BALTI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08651 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Monipur Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000954/2021-2022 | 2150/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 0 | 0 | 1
Total | [13 empty] | 75.15 | 0 | 0