## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of EOJNAGAR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08655 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Eojnagar Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001249/2021-2022 | 403/BD | 10/02/2022 | 27/03/2022 | UTPAL CONSTRUCTION & CO. | 91.51 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of EOJNAGAR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08655 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for EOJNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001955/2021-2022 | 306/BHTSD | 07/03/2022 | 22/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.94 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of EOJNAGAR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | SM/08655 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 2990/BD | 29/09/2022 | 29/09/2022 | Resource Division | 0.02 | 0 | 0 | 0
Total | [13 empty] | 95.46 | 0 | 0