## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kachua Swarupnagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08660 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Kachua Swarupnagar Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000333/2021-2022 | 1654/BD | 07/09/2021 | 22/10/2021 | UTPAL CONSTRUCTION & CO. | 86.71 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kachua Swarupnagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | SM/08660 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for KACHUA SWARUPNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001957/2021-2022 | 308/BHTSD | 07/03/2022 | 22/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.29 | 0 | 0 | 1
Total | [13 empty] | 91 | 0 | 0