## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. | SM/08690 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Gokna Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.03 | Assistant Engineer |  | ORD/001054/2021-2022 | 669/BST | 24/12/2021 | 27/12/2021 | M/S LAXMI ENTERPRISE | 4.83 | 1.64 | 34.02 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. | SM/08690 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Bagdah Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.07 | Assistant Engineer |  | ORD/001058/2021-2022 | 673/BST | 24/12/2021 | 24/03/2022 | LAB. SOLUTION | 4.83 | 3.66 | 75.66 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. | SM/08690 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Haroa Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.02 | Assistant Engineer |  | ORD/001053/2021-2022 | 668/BST | 24/12/2021 | 24/03/2022 | M/S LAXMI ENTERPRISE | 4.83 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. | SM/08690 | Support-WQMSP | Purchase of Chemical for water testing & NABL accreditation of District Laboratory under Barasat Sub Division, P.H.E. Dte. PART-C. | Assistant Engineer |  | ORD/002070/2021-2022 | 761/BSD | 25/11/2021 | 02/12/2021 | LAB. SOLUTION | 3.57 | 2.92 | 81.93 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. | SM/08690 | Support-WQMSP | Purchase of Chemical for water testing & NABL accreditation of District Laboratory under Barasat Sub Division, P.H.E. Dte. PART-A Sl No.-1 | Assistant Engineer |  | ORD/002045/2021-2022 | 714/BSD | 08/10/2021 | 15/10/2021 | LAB. SOLUTION | 1.62 | 1.62 | 100 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. | SM/08690 | Support-WQMSP | Purchase of Chemical for water testing & NABL accreditation of District Laboratory under Barasat Sub Division, P.H.E. Dte. PART-B Sl No.-2 | Assistant Engineer |  | ORD/002046/2021-2022 | 715/BSD | 08/10/2021 | 15/10/2021 | LAB. SOLUTION | 3.51 | 3.51 | 100 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. | SM/08690 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Basirhat Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.01 | Assistant Engineer |  | ORD/001052/2021-2022 | 667/BST | 24/12/2021 | 24/03/2022 | M/S LAXMI ENTERPRISE | 4.83 | 3.66 | 75.66 | 0
Total | [13 empty] | 28.03 | 17.01 | 60.69