## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. | SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Bodai Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.05 | Assistant Engineer |  | ORD/001056/2021-2022 | 671/BST | 24/12/2021 | 27/12/2021 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 3.64 | 75.66 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. | SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Habra Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.04 | Assistant Engineer |  | ORD/001055/2021-2022 | 670/BST | 24/12/2021 | 24/03/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 3.64 | 75.66 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. | SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Bishnupur Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.06 | Assistant Engineer |  | ORD/001057/2021-2022 | 672/BST | 24/12/2021 | 24/03/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 3.64 | 75.66 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. | SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Gokna Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.03 | Assistant Engineer |  | ORD/001054/2021-2022 | 669/BST | 24/12/2021 | 27/12/2021 | M/S LAXMI ENTERPRISE | 4.83 | 0.77 | 15.87 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. | SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Basirhat Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.01 | Assistant Engineer |  | ORD/001052/2021-2022 | 667/BST | 24/12/2021 | 24/03/2022 | M/S LAXMI ENTERPRISE | 4.83 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. | SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Haroa Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.02 | Assistant Engineer |  | ORD/001053/2021-2022 | 668/BST | 24/12/2021 | 24/03/2022 | M/S LAXMI ENTERPRISE | 4.83 | 3.66 | 75.66 | 0
Total | [13 empty] | 28.92 | 15.33 | 53.03