## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khulna Bhanderkhali Piped Water Supply Scheme (Zone-I), Sandeshkhali-II Block (Phase-I) | SM/08762 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Khulna Bhandarkhali (Zone-I) Water Supply scheme Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000482/2021-2022 | 1740/BD | 14/09/2021 | 29/10/2021 | M/S B.K.ENTERPRISE. | 76.95 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khulna Bhanderkhali Piped Water Supply Scheme (Zone-I), Sandeshkhali-II Block (Phase-I) | SM/08762 | Retrofitting | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Khulna Bhanderkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001719/2021-2022 | 1981/HSD | 02/12/2021 | 12/12/2021 | M/S NIRMAN CONSTRUCTION. | 3.54 | 0 | 0 | 1
Total | [13 empty] | 80.49 | 0 | 0