## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Durgamandop Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | SM/08764 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Durgamandop Water Supply scheme Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000481/2021-2022 | 1739/BD | 14/09/2021 | 29/10/2021 | M/S B.K.ENTERPRISE. | 77.69 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Durgamandop Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | SM/08764 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001018/2023-2024 | 1062/HSD | 31/08/2023 | 10/09/2023 | ANKUSH CONSTRUCTION & CO. | 0.97 | 0 | 0 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Durgamandop Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | SM/08764 | Retrofitting | Acceptance cum work order for construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection for augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001440/2024-2025 | 110/BD | 09/01/2025 | 25/03/2025 | MD.SALIM GAZI. | 11.68 | 0 | 0 | 0
Total | [13 empty] | 90.35 | 0 | 0