## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | SM/08765 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Fakirtakia mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Fakirtakia w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001113/2021-2022 | 180/BD | 20/01/2022 | 06/03/2022 | R.K.MANDAL AND CO. | 74.88 | 74.79 | 99.88 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | SM/08765 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001762/2021-2022 | 472/HSD | 10/03/2022 | 20/03/2022 | M/S MITRA CONSTRUCTION. | 3.89 | 3.89 | 99.8 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | SM/08765 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001761/2021-2022 | 471/HSD | 10/03/2022 | 20/03/2022 | JESMINE ENTERPRISE. | 3.82 | 3.82 | 99.96 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | SM/08765 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 1821/BD | 19/06/2023 | 19/06/2023 | Resource Division | 16.88 | 0 | 0 | 0
Total | [13 empty] | 99.47 | 82.49 | 82.93