## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Boyermari Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | SM/08766 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Boyermari Abad Water Supply scheme Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000477/2021-2022 | 1738/BD | 14/09/2021 | 29/10/2021 | DEBAPRASAD MONDAL. | 81.09 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Boyermari Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | SM/08766 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 1812/BD | 19/06/2023 | 19/06/2023 | Resource Division | 16.51 | 0 | 0 | 0
Total | [13 empty] | 97.6 | 0 | 0