## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Piped Water Supply Scheme, Swarupnagar Block under Barasat Division, P.H.E.Dte. (Phase-II) | SM/08769 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Dobila Piped Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase II) | Assistant Engineer | Junior Engineer | ORD/000567/2021-2022 | 1954/BD | 08/10/2021 | 23/10/2021 | M/S SUKANTA ENTERPRISE. | 14.73 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Piped Water Supply Scheme, Swarupnagar Block under Barasat Division, P.H.E.Dte. (Phase-II) | SM/08769 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Matiagacha W/S Scheme in Habra - II Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002025/2021-2022 | 128/HAB | 16/03/2022 | 26/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.35 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Piped Water Supply Scheme, Swarupnagar Block under Barasat Division, P.H.E.Dte. (Phase-II) | SM/08769 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 2863/BD | 21/09/2022 | 21/09/2022 | Resource Division | 3.08 | 0 | 0 | 0
Total | [13 empty] | 21.17 | 0 | 0