## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Piped Water Supply Scheme, Basirhat-II Block under Barasat Division, P.H.E.Dte. (Phase-II) | SM/08772 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Joypur Gopmahal Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase II) | Assistant Engineer | Junior Engineer | ORD/000563/2021-2022 | 1951/BD | 08/10/2021 | 23/10/2021 | SHIBU BISWAS. | 21.73 | 20.05 | 92.26 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Piped Water Supply Scheme, Basirhat-II Block under Barasat Division, P.H.E.Dte. (Phase-II) | SM/08772 | Retrofitting | Sinking of 300 Mtr.Deep 100X40 mm dia Trial- cum-production Tube-Well fitting with PVC Pipes and strainer with Indian Mark-II at Joypur Gopmahal of Basirhat-II Block under Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002657/2021-2022 | 1111/ BHT SD | 27/08/2021 | 16/09/2021 | M/S MAA TARA ENTERPRISE | 2.34 | 1.95 | 83.53 | 1
Total | [13 empty] | 24.07 | 22 | 91.42