## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamarpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08774 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Kamarpur & its adjoining mouzas Water Supply Scheme at Habra-II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000754/2021-2022 | 2390/BD | 09/12/2021 | 23/01/2022 | SHIBU BISWAS. | 53.39 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamarpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08774 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Dakshin Bhebia Zone-II Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001001/2021-2022 | 2181/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.93 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamarpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08774 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Bergum W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000970/2021-2022 | 571/HAB | 23/12/2021 | 02/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.71 | 0 | 0 | 1
Total | [13 empty] | 62.03 | 0 | 0