## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08775 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Chaital Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000967/2021-2022 | 2164/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.49 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08775 | Retrofitting | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) from existing distribution system at Bergum Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte.( For balance work of Retrofitting). | Assistant Engineer | Junior Engineer | ORD/000837/2022-2023 | 3582/ BD | 08/12/2022 | 07/01/2023 | ANKUSH CONSTRUCTION & CO. | 16.19 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08775 | Retrofitting | Continuation work order for Hiring Diesel Luxury Car on Daily basis (for 6 months from 01.04.2023 to 30.06.2023) for the office use of the Executive Engineer, Barasat Division, PHE Dte | Assistant Engineer |  | ORD/001306/2022-2023 | 1044/BD | 31/03/2023 | 30/06/2023 | MADHAB CHANDRA DAS | 0.45 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08775 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 250/BD | 27/01/2022 | 27/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08775 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Bergum Water Supply Scheme at Habra-I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000864/2021-2022 | 2484/BD | 17/12/2021 | 19/02/2027 | UNICON INDIA. | 163.67 | 0 | 0 | 100
Total | [13 empty] | 186.79 | 0 | 0