## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-I) at Habra-I Block (Phase-I) | SM/08778 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Sindrani (Zone-II) Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/001116/2021-2022 | 610/Bon | 31/12/2021 | 20/01/2022 | UMWELT ENGINEER PVT.LTD. | 3.48 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-I) at Habra-I Block (Phase-I) | SM/08778 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Maslandapur Water Supply Scheme(Zone-I) at Habra-I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000816/2021-2022 | 2436/BD | 13/12/2021 | 13/03/2022 | SUPRITI ENTERPRISE. | 113.29 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-I) at Habra-I Block (Phase-I) | SM/08778 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 249/BD | 27/01/2022 | 27/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
Total | [13 empty] | 118.76 | 0 | 0