## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-II) at Habra-I Block (Phase-I) | SM/08779 | Retrofitting | Formal Work Order cor Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MASLANDAPUR Water Supply Scheme(ZONE-II) at Habra - I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I). | Assistant Engineer | Junior Engineer | ORD/000944/2021-2022 | 01/BD | 03/01/2022 | 03/04/2022 | M/S B.K.ENTERPRISE. | 145.09 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-II) at Habra-I Block (Phase-I) | SM/08779 | Retrofitting | Preparation of geo-referenced GIS mapping with integrated software showing georeferenced location of Households, Piped water supply scheme and Distribution network to be incorporated into map by using both GIS & CAD software keeping the essential Technical aspect of 6 numbers scheme namely Gobindapur Dhokra, Rajnagar, Sadiknagar Zone-I, Bithari Zone-I, Bithari Zone-II and Simla Durgapur of North 24 Pgs. District under the jurisdiction of Basirhat Sub-Division. | Assistant Engineer | Junior Engineer | ORD/000551/2022-2023 | 945 / BHT SD | 19/07/2022 | 03/08/2022 | M/S TECHVISION. | 2.91 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-II) at Habra-I Block (Phase-I) | SM/08779 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 251/BD | 27/01/2022 | 27/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
Total | [13 empty] | 149.98 | 0 | 0