## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Janaphul Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08780 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Janaphul Water Supply Scheme at Habra-I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000753/2021-2022 | 2389/BD | 09/12/2021 | 23/01/2022 | ORIENT CONSTRUCTION. | 72.42 | 67.56 | 93.28 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Janaphul Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08780 | Retrofitting | Acceptance cum work order for Supply of Mechanized boat on hire basis with providing driver, helper and other requirement as per terms condition and specification as per direction of the EIC under Hasnabad Sub-Division, P.H.E. Dte. Period : 01.08.2022 to 31.07.2023 = 365 days. | Assistant Engineer | Junior Engineer | ORD/000224/2022-2023 | 1118/HSD | 08/07/2022 | 09/07/2022 | RANJIT KUMAR MANDAL. | 3.23 | 11.93 | 369.28 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Janaphul Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08780 | Retrofitting | Acceptance cum Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B. | Assistant Engineer |  | ORD/001180/2023-2024 | 253/BKP | 31/07/2023 | 31/01/2024 | GOPAL SINGHA. | 0.87 | 0.67 | 76.26 | 40
Total | [13 empty] | 76.53 | 80.15 | 104.74