## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadpur Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08781 | Retrofitting | Acceptance cum work order for Restoration of different diameter existing pipe lines by laying UPVC pipes and allied works of Sadpur W/S scheme due to up gradation of different roads within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/003033/2021-2022 | 2047//BD | 21/09/2021 | 21/10/2021 | MONDAL ENTERPRISE. (BARASAT) | 26.59 | 0 | 0 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadpur Piped Water Supply Scheme at Habra-I Block (Phase-I) | SM/08781 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SADPUR Water Supply Scheme at Habra - I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000592/2022-2023 | 2627/BD | 05/09/2022 | 26/06/2024 | M/S SUKANTA ENTERPRISE. | 48.49 | 0 | 0 | 100
Total | [13 empty] | 75.08 | 0 | 0