## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bira Rajibpur Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08782 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Ashari Narayanpur Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000987/2021-2022 | 2170/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.59 | 99.56 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bira Rajibpur Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08782 | Retrofitting | Formal Work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIRA RAJIBPUR Water Supply Scheme at Habra -II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000914/2021-2022 | 2623/BD | 27/12/2021 | 27/03/2022 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 189.09 | 156.26 | 82.63 | 1
Total | [13 empty] | 192.7 | 159.85 | 82.95