## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kankpul Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08783 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Kankpul Water Supply Scheme at Habra-II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000752/2021-2022 | 2388/BD | 09/12/2021 | 23/01/2022 | S.S.ENTERPRISE. (BAMANGACHI) | 82.85 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kankpul Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08783 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Korakati Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000990/2021-2022 | 2172/HSD | 28/12/2021 | 18/01/2022 | UMWELT ENGINEER PVT.LTD. | 4.12 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kankpul Piped Water Supply Scheme at Habra-II Block (Phase-I) | SM/08783 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Kankpul W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000939/2021-2022 | 567/HAB | 22/12/2021 | 01/01/2022 | UMWELT ENGINEER PVT.LTD. | 4.02 | 0 | 0 | 1
Total | [13 empty] | 90.99 | 0 | 0