## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Magurali Piped Water Supply Scheme at Baduria Block (Phase-I) | SM/08785 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area under Magurali Water Supply Scheme at Baduria Block, District- North 24 Parganas under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000823/2021-2022 | 2439/BD | 13/12/2021 | 13/03/2022 | UTPAL CONSTRUCTION & CO. | 232.79 | 205.13 | 88.12 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Magurali Piped Water Supply Scheme at Baduria Block (Phase-I) | SM/08785 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for MAGURALI Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001978/2021-2022 | 350/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.96 | 4.96 | 100 | 1
Total | [13 empty] | 237.75 | 210.09 | 88.36