## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Itinda Panitor Piped Water Supply Scheme at Basirhat-I Block (Phase-I) | SM/08786 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Itinda Panitar Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000912/2021-2022 | 2622/BD | 27/12/2021 | 27/03/2022 | SUBHASH BOSE. | 171.59 | 164.59 | 95.92 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Itinda Panitor Piped Water Supply Scheme at Basirhat-I Block (Phase-I) | SM/08786 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for ITINDA PANITOR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001933/2021-2022 | 189/BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Itinda Panitor Piped Water Supply Scheme at Basirhat-I Block (Phase-I) | SM/08786 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000177/2022-2023 | 598/BD | 23/02/2023 | 23/02/2023 | Resource Division | 22.18 | 0 | 0 | 0
Total | [13 empty] | 198.61 | 169.43 | 85.31