## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Resource | Engagement of implementation support agency (ISA) for implementation of community mobilization and capacity building activities under Jal Jeevan Mission (JJM) support activities at North 24 Parganas District | SM/08991 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the North 24 Pgs . |  | Junior Engineer | ORD/000789/2022-2023 | 446/RS | 02/02/2023 | 02/09/2023 | IMAGIN | 251.88 | 251.88 | 100 | 50
2 | NORTH 24 PARGANAS |  | Resource | Engagement of implementation support agency (ISA) for implementation of community mobilization and capacity building activities under Jal Jeevan Mission (JJM) support activities at North 24 Parganas District | SM/08991 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the North 24 Parganas District. | Assistant Engineer | Junior Engineer | ORD/000139/2022-2023 | 2854/RS | 20/05/2022 | 17/10/2022 | HALDAH EASTERN DEVELOPMENT SOCIETY | 223.78 | 212.77 | 95.08 | 95
Total | [13 empty] | 475.67 | 464.65 | 97.69