## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Construction of RCC stand post at different places & other allied works for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001071/2021-2022 | 631/HSD(CAMP) | 29/06/2021 | 06/07/2021 | M/S NIRMAN CONSTRUCTION. | 4.3 | 4.3 | 100 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Milon Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-F) | Assistant Engineer | Junior Engineer | ORD/000764/2021-2022 | 592/HSD(Camp) | 29/06/2021 | 06/07/2021 | DEB PRASAD GHOSH. | 4.26 | 4.22 | 99.04 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Asarani Das at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-G) | Assistant Engineer | Junior Engineer | ORD/000765/2021-2022 | 593/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S GHOSH CONSTRUCTION. | 4.12 | 4.09 | 99.13 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at near pond of Roti Howly, Probodh Mondal, & Ramen Mondal to Balaram Mondal due to cyclone "YAAS" for Bhabanipur- I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000771/2021-2022 | 599/HSD(Camp) | 29/06/2021 | 06/07/2021 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 3.98 | 3.96 | 99.68 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Bouthakurani w/s Scheme (Z-I to V), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000836/2021-2022 | 640/HSD (Camp) | 30/06/2021 | 07/07/2021 | SARKAR ENTERPRISE & CO. | 4.53 | 4.51 | 99.54 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Bouthakurani w/s Scheme (Zone-I to V), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000838/2021-2022 | 642/HSD (Camp) | 30/06/2021 | 07/07/2021 | R.K.MANDAL AND CO. | 4.81 | 4.81 | 100 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Hingalganj w/s Scheme (Old), Hingalganj Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000776/2021-2022 | 604/HSD(Camp) | 29/06/2021 | 06/07/2021 | MONDAL & CO. (BASIRHAT). | 1.93 | 1.93 | 99.58 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC/HDPE pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-IV to VI), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000855/2021-2022 | 659/HSD(Camp) | 30/06/2021 | 07/07/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.38 | 4.37 | 99.67 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Sandeshkhali w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000856/2021-2022 | 660/HSD(Camp) | 30/06/2021 | 07/07/2021 | MONDAL & CO. (BASIRHAT). | 4.53 | 4.53 | 100 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Laying of 110 mm dia HDPE waste water disposal pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-3), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000787/2021-2022 | 615/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S RAJPATH CONSTRUCTION. | 4.83 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm dia. UPVC pipe for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" within Taki Municipal w/s scheme (Zone-II), Taki Municipality under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000780/2021-2022 | 608/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S RAJPATH CONSTRUCTION. | 3.5 | 3.49 | 99.9 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Laying of different dia PVC distribution pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-16, 19 & 23), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000781/2021-2022 | 609/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S RAJPATH CONSTRUCTION. | 4.79 | 3.35 | 69.91 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Kartick Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-H) | Assistant Engineer | Junior Engineer | ORD/001069/2021-2022 | 594/HSD(Camp) | 29/06/2021 | 06/07/2021 | GOBINDA DAS. | 3.95 | 3.93 | 99.4 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Laying of 110 mm dia HDPE waste water disposal pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-3), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000788/2021-2022 | 616/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S RAJPATH CONSTRUCTION. | 3.35 | 3.35 | 100 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of different dia. HDPE distribution pipe line from CWR to Jagananda Ashram for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000793/2021-2022 | 620/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S B.K.ENTERPRISE. | 4.39 | 4.39 | 100 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC/HDPE pipe line at different places due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000795/2021-2022 | 622/HSD(Camp) | 29/06/2021 | 06/07/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.55 | 4.55 | 100 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. UPVC distribution pipe line from near N/H/O Tapas Mallick to near Khargeshwar Adibasi FP School at Mithhakhali for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000802/2021-2022 | 629/HSD(Camp) | 29/06/2021 | 06/07/2021 | R.K.MANDAL AND CO. | 4.67 | 4.67 | 100 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. UPVC distribution pipe line from near Monipur Bazar to N/H/O Dinabandhu Mondal & Chimta Hatkhola to N/H/O Chittaranjan Das for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000803/2021-2022 | 630/HSD(Camp) | 29/06/2021 | 06/07/2021 | R.K.MANDAL AND CO. | 4.77 | 4.77 | 100 | 0
19 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Construction of RCC stand post at different places & other allied works for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001012/2021-2022 | 631/HSD(CAMP) | 29/06/2021 | 06/07/2021 | M/S NIRMAN CONSTRUCTION. | 4.3 | 0 | 0 | 0
20 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Kartick Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-H) | Assistant Engineer | Junior Engineer | ORD/001018/2021-2022 | 594/HSD(Camp) | 29/06/2021 | 06/07/2021 | GOBINDA DAS. | 3.95 | 0 | 0 | 0
21 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Chotto Sehara w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000841/2021-2022 | 645/HSD (Camp) | 30/06/2021 | 07/07/2021 | MONDAL & CO. (BASIRHAT). | 4.8 | 4.8 | 100 | 0
22 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Baunia Abad w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000842/2021-2022 | 646/HSD (Camp) | 30/06/2021 | 07/07/2021 | M/S PROGATI ENTERPRISE. | 4.53 | 4.53 | 100 | 0
23 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia. UPVC distribution pipe line from near Avijan Sangha to Kachari Bari & from near Radharani High School to N/H/O Shyam Singh for damage portion due to cyclone 'YAAS' within Sandeshkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000846/2021-2022 | 650/HSD(Camp) | 30/06/2021 | 07/07/2021 | FIDERE MARINE SERVICES PVT. LLTD. | 4.88 | 4.88 | 100 | 0
24 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Sandeshkhali w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000847/2021-2022 | 651/HSD(Camp) | 30/06/2021 | 07/07/2021 | RAM CHANDRA HAZRA. | 4.57 | 4.56 | 99.84 | 0
25 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by Laying of diff. dia. HDPE distribution pipe line due to cyclone YAAS in different Mouza within Hasnabad w/s scheme, Hasnabad Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000877/2021-2022 | 665/HSD(Camp) | 30/06/2021 | 07/07/2021 | ROY CHOWDHURY CONSTRUCTION. | 4.49 | 4.49 | 100 | 0
26 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Sandeshkhali w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000848/2021-2022 | 652/HSD(Camp) | 30/06/2021 | 07/07/2021 | ABDUL HAMID GAZI. | 4.52 | 4.53 | 100.06 | 0
27 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Gabberia w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000849/2021-2022 | 653/HSD(Camp) | 30/06/2021 | 07/07/2021 | MONDAL & CO. (BASIRHAT). | 4.59 | 4.59 | 100 | 0
28 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-IV to VI), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000852/2021-2022 | 656/HSD(Camp) | 30/06/2021 | 07/07/2021 | R.K.MANDAL AND CO. | 4.71 | 4.71 | 100 | 0
29 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Laying of 110 mm dia HDPE waste water disposal pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-3), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001033/2021-2022 | 615/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S RAJPATH CONSTRUCTION. | 4.83 | 0 | 0 | 0
30 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Mukul Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000759/2021-2022 | 587/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S GHOSH CONSTRUCTION. | 4.06 | 4.05 | 99.53 | 0
31 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Sasanka Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-J) | Assistant Engineer | Junior Engineer | ORD/000768/2021-2022 | 596/HSD(Camp) | 29/06/2021 | 06/07/2021 | NIKHIL SAMADDAR | 3.97 | 3.95 | 99.67 | 0
32 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling near pond of Dr. Pronab Roy, Shambhu Dolui, Md. Rahamat & Firoj Molla due to cyclone "YAAS" for Bhabanipur-I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000769/2021-2022 | 597/HSD(Camp) | 29/06/2021 | 06/07/2021 | NIKHIL SAMADDAR | 4.09 | 4.03 | 98.6 | 0
33 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at near pond of Jagadish Mondal, Baidyanath Mondal, Madhu Mondal, Santosh Sau & Bablu Roy due to cyclone "YAAS" for Bhabanipur-II GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000770/2021-2022 | 598/HSD(Camp) | 29/06/2021 | 06/07/2021 | ABDUL ALIM MONDAL. | 4.05 | 4.04 | 99.86 | 0
34 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Hingalganj w/s Scheme (Zone-I), Hingalganj Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000777/2021-2022 | 605/HSD(Camp) | 29/06/2021 | 06/07/2021 | MONDAL & CO. (BASIRHAT). | 3.94 | 3.93 | 99.75 | 0
35 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order forProtection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Goutam Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000760/2021-2022 | 588/HSD(Camp) | 29/06/2021 | 06/07/2021 | GOBINDA DAS. | 3.94 | 3.91 | 99.2 | 0
36 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Tushar Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000761/2021-2022 | 589/HSD(Camp) | 29/06/2021 | 06/07/2021 | MD.SALIM GAZI. | 4.11 | 4.06 | 98.98 | 0
37 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by bamboo pilling at different places due to cyclone "YAAS" within Taki Municipal w/s scheme (Zone-II), Taki Municipality under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000778/2021-2022 | 606/HSD(Camp) | 29/06/2021 | 06/07/2021 | R.K.MANDAL AND CO. | 4.75 | 4.74 | 99.7 | 0
38 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Laying of 110 mm dia HDPE waste water disposal pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-3), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001072/2021-2022 | 615/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S RAJPATH CONSTRUCTION. | 4.83 | 4.83 | 100 | 0
39 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at different places due to cyclone "YAAS" within Taki Municipal w/s scheme (Zone-II), Taki Municipality under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000779/2021-2022 | 607/HSD(Camp) | 29/06/2021 | 06/07/2021 | R.K.MANDAL AND CO. | 4.85 | 4.83 | 99.66 | 0
40 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Bermajur w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000783/2021-2022 | 611/HSD(Camp) | 29/06/2021 | 06/07/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.81 | 4.81 | 100 | 0
41 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by Bamboo pilling at different places due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000785/2021-2022 | 613/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S NIRMAN CONSTRUCTION. | 4.77 | 4.76 | 99.92 | 0
42 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new different dia. UPVC pipe for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" within Taki Municipal w/s scheme (Zone-II), Taki Municipality under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000786/2021-2022 | 614/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S RAJPATH CONSTRUCTION. | 3.45 | 3.45 | 99.76 | 0
43 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Baunia Abad w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000843/2021-2022 | 647/HSD (Camp) | 30/06/2021 | 07/07/2021 | P & S ASSOCIATES. | 4.52 | 4.52 | 99.87 | 0
44 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Durgamandop w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000844/2021-2022 | 648/HSD (Camp) | 30/06/2021 | 07/07/2021 | ABDUL ALIM MONDAL. | 4.52 | 4.51 | 99.73 | 0
45 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-I to III), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000853/2021-2022 | 657/HSD(Camp) | 30/06/2021 | 07/07/2021 | R.K.MANDAL AND CO. | 4.79 | 4.79 | 100 | 0
46 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC/HDPE pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-I to III), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000854/2021-2022 | 658/HSD(Camp) | 30/06/2021 | 07/07/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.38 | 4.37 | 99.75 | 0
47 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 75 mm dia. HDPE distribution pipe line from near Sitalia FP School to N/H/O Mrityunjoy Baulia & N/H/O Sudhansu Biswas for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000790/2021-2022 | 617/HSD(Camp) | 29/06/2021 | 06/07/2021 | CHITTA RANJAN MONDAL. | 4.79 | 4.79 | 100 | 0
48 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 160mm dia. HDPE distribution pipe line from CWR to Jagananda Ashram for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000794/2021-2022 | 621/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S B.K.ENTERPRISE. | 4.91 | 4.91 | 100 | 0
49 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at N/H/O Nemai Sardar, near Monipur Bazar & other different places due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000806/2021-2022 | 633/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S PROGATI ENTERPRISE. | 4.24 | 4.25 | 100.07 | 0
50 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Durgamandop w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001302/2021-2022 | 648/HSD (Camp) | 30/06/2021 | 07/07/2021 | ABDUL ALIM MONDAL. | 4.52 | 0 | 0 | 0
51 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Ashu Das at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000762/2021-2022 | 590/HSD(Camp) | 29/06/2021 | 06/07/2021 | PRITAM MUKHOPADHYAY. | 4.17 | 4.1 | 98.21 | 0
52 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Bhuban Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000763/2021-2022 | 591/HSD(Camp) | 29/06/2021 | 06/07/2021 | TAKI ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.02 | 3.99 | 99.26 | 0
53 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Bouthakurani w/s Scheme (Zone-I to V), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001560/2021-2022 | 641/HSD (Camp) | 30/06/2021 | 07/07/2021 | R.K.MANDAL AND CO. | 4.69 | 4.69 | 100 | 0
54 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Protim Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-I) | Assistant Engineer | Junior Engineer | ORD/000767/2021-2022 | 595/HSD(Camp) | 29/06/2021 | 06/07/2021 | MD.SALIM GAZI. | 4.08 | 4.03 | 98.86 | 0
55 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Hingalganj w/s Scheme (Zone-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000782/2021-2022 | 610/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S NIRMAN CONSTRUCTION. | 4.81 | 4.81 | 100 | 0
56 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. UPVC distribution pipe line from near N/H/O Tapas Mallick to near Khargeshwar Adibasi FP School at Mithhakhali for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000801/2021-2022 | 628/HSD(Camp) | 29/06/2021 | 06/07/2021 | R.K.MANDAL AND CO. | 4.77 | 4.77 | 100 | 0
57 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Bouthakurani w/s Scheme (Zone-I to V), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001303/2021-2022 | R.K.MANDAL AND CO | 30/06/2021 | 07/07/2021 | R.K.MANDAL AND CO. | 4.69 | 0 | 0 | 0
58 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at near PH No-1 & N/H/O Ramkrishna Bhuiya due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000805/2021-2022 | 632/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S DATTA ENTERPRISE. | 4.24 | 4.23 | 99.81 | 0
59 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Chotto Sehara w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. (Part -B) | Assistant Engineer | Junior Engineer | ORD/000840/2021-2022 | 644/HSD (Camp) | 30/06/2021 | 07/07/2021 | MONDAL & CO. (BASIRHAT). | 4.86 | 4.86 | 100 | 0
60 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Chotto Sehara w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. (Part -A) | Assistant Engineer | Junior Engineer | ORD/000839/2021-2022 | 643/HSD (Camp) | 30/06/2021 | 07/07/2021 | MONDAL & CO. (BASIRHAT). | 4.56 | 4.56 | 100 | 0
61 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of different dia. HDPE distribution pipe line from N/H/O Shambhu Mondal to near Khulna Bachar para more for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part B) | Assistant Engineer | Junior Engineer | ORD/000797/2021-2022 | 624/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S B.K.ENTERPRISE. | 4.89 | 4.89 | 100 | 0
62 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 110 mm dia. UPVC distribution pipe line from near N/H/O Amar Bera at Mithakhali to near Chimta Chowmatha for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000799/2021-2022 | 626/HSD(Camp) | 29/06/2021 | 06/07/2021 | R.K.MANDAL AND CO. | 4.81 | 4.81 | 100 | 0
63 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 110 mm dia. UPVC distribution pipe line from near N/H/O Amar Bera at Mithakhali to near Chimta Chowmatha for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000800/2021-2022 | 627/HSD(Camp) | 29/06/2021 | 06/07/2021 | R.K.MANDAL AND CO. | 4.67 | 4.67 | 100 | 0
64 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 75mm dia UPVC pipe from Sulkuni Jogendra Maity School to Sulkuni Howly para for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur-I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000772/2021-2022 | 600/HSD(Camp) | 29/06/2021 | 06/07/2021 | ABDUL ALIM MONDAL. | 4.81 | 4.8 | 99.94 | 0
65 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-III to IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000857/2021-2022 | 661/HSD(Camp) | 30/06/2021 | 07/07/2021 | M/S DATTA ENTERPRISE. | 4.68 | 4.68 | 100 | 0
66 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-I to II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000858/2021-2022 | 662/HSD(Camp) | 30/06/2021 | 07/07/2021 | M/S PROGATI ENTERPRISE. | 4.55 | 4.55 | 100 | 0
67 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. HDPE distribution pipe line from N/H/O Hemanta Sarkar to N/H/O Khokan Mondal at Dk. Hatgacha for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000791/2021-2022 | 618/HSD(Camp) | 29/06/2021 | 06/07/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.89 | 4.89 | 100 | 0
68 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 110mm dia. HDPE distribution pipe line from Hatgacha Sarkar para more to N/H/O Hemanta Sarkar for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000792/2021-2022 | 619/HSD(Camp) | 29/06/2021 | 06/07/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.84 | 4.84 | 100 | 0
69 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 110 mm dia. HDPE distribution pipe line from N/H/O Shambhu Mondal to near Khulna Bachar para more for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part A) | Assistant Engineer | Junior Engineer | ORD/000796/2021-2022 | 623/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S B.K.ENTERPRISE. | 4.83 | 4.83 | 100 | 0
70 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm dia UPVC pipe from N/H/O Santosh Sau to Roti Howly for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur- I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002072/2021-2022 | 602/HSD(Camp) | 29/06/2021 | 06/07/2021 | BADAL GHOSH. | 4.15 | 4.14 | 99.83 | 0
71 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm & 75mm dia UPVC pipe at different places for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur-I & II GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002071/2021-2022 | 601/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S K.B.ENTERPRISE. | 3.72 | 3.7 | 99.59 | 0
72 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-III to IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000860/2021-2022 | 664/HSD(Camp) | 30/06/2021 | 07/07/2021 | M/S PROGATI ENTERPRISE. | 4.84 | 4.84 | 100 | 0
73 | NORTH 24 PARGANAS |  | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. | SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-I to II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000859/2021-2022 | 663/HSD(Camp) | 30/06/2021 | 07/07/2021 | M/S DATTA ENTERPRISE. | 4.84 | 4.84 | 100 | 0
Total | [13 empty] | 323.54 | 294.37 | 90.98