## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000412/2021-2022 | 428/HSD(Camp) | 27/05/2021 | 04/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.77 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Jeliakhali GP from 27.05.21 to 02.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000417/2021-2022 | 433/HSD(Camp) | 27/05/2021 | 03/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.62 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 27.05.21 to 28.05.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000394/2021-2022 | 411/HSD(Camp) | 27/05/2021 | 29/05/2021 | M/S PROGATI ENTERPRISE. | 4.94 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 29.05.21 to 03.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000395/2021-2022 | 412/HSD(Camp) | 27/05/2021 | 02/06/2021 | M/S PROGATI ENTERPRISE. | 4.85 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-II GP from 27.05.21 to 03.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000403/2021-2022 | 420/HSD(Camp) | 27/05/2021 | 04/06/2021 | M/S PROGATI ENTERPRISE. | 4.93 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalitala GP from 18.06.21 to 30.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000529/2021-2022 | 566/HSD(Camp) | 14/06/2021 | 27/06/2021 | M/S PROGATI ENTERPRISE. | 4.72 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 05.06.21 to 11.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000441/2021-2022 | 472/HSD(Camp) | 03/06/2021 | 10/06/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.85 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-I GP from 05.06.21 to 18.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000447/2021-2022 | 478/HSD(Camp) | 03/06/2021 | 17/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.67 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-II GP from 05.06.21 to 18.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000448/2021-2022 | 479/HSD(Camp) | 03/06/2021 | 17/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.67 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 04.06.21 to 09.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000449/2021-2022 | 480/HSD(Camp) | 03/06/2021 | 09/06/2021 | M/S DATTA ENTERPRISE. | 4.85 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 1, 2, 3, 4 from 03.06.21 to 14.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000464/2021-2022 | 495/HSD(Camp) | 03/06/2021 | 15/06/2021 | M/S RAJPATH CONSTRUCTION. | 4.61 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalitala GP from 05.06.21 to 17.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer |  | ORD/000466/2021-2022 | 497/HSD(Camp) | 03/06/2021 | 16/06/2021 | M/S PROGATI ENTERPRISE. | 4.73 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-I GP from 04.06.21 to 15.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000454/2021-2022 | 485/HSD(Camp) | 03/06/2021 | 15/06/2021 | M/S DATTA ENTERPRISE. | 4.92 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 03.06.21 to 12.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer |  | ORD/000463/2021-2022 | 494/HSD(Camp) | 03/06/2021 | 13/06/2021 | TRISHA ENTERPRISE & CO. | 4.56 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bishpur GP from 10.06.21 to 18.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000472/2021-2022 | 503/HSD(Camp) | 03/06/2021 | 12/06/2021 | TRISHA ENTERPRISE & CO. | 4.67 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-II GP from 27.05.21 to 04.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000419/2021-2022 | 435/HSD(Camp) | 27/05/2021 | 05/06/2021 | S.K.ENTERPRISE. | 4.66 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sarberia Agarhati GP from 27.05.21 to 02.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000405/2021-2022 | 422/HSD(Camp) | 27/05/2021 | 03/06/2021 | M/S PROGATI ENTERPRISE. | 4.77 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 29.05.21 to 04.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000410/2021-2022 | 426/HSD(Camp) | 27/05/2021 | 03/06/2021 | S.K.ENTERPRISE. | 4.86 | 0 | 0 | 0
19 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000411/2021-2022 | 427/HSD(Camp) | 27/05/2021 | 30/05/2021 | M/S NIRMAN CONSTRUCTION. | 4.49 | 0 | 0 | 0
20 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bishpur GP from 27.05.21 to 31.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2021-2022 | 441/HSD(Camp) | 27/05/2021 | 01/06/2021 | MONDAL & CO. (BASIRHAT). | 4.53 | 0 | 0 | 0
21 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 27.05.21 to 30.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000423/2021-2022 | 439/HSD(Camp) | 27/05/2021 | 31/05/2021 | M/S PROGATI ENTERPRISE. | 4.71 | 0 | 0 | 0
22 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 15 & 16 from 27.05.21 to 01.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2021-2022 | 442/HSD(Camp) | 27/05/2021 | 02/06/2021 | M/S RAJPATH CONSTRUCTION. | 4.68 | 0 | 0 | 0
23 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 1, 2, 3, 4 from 27.05.21 to 02.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2021-2022 | 443/HSD(Camp) | 27/05/2021 | 03/06/2021 | M/S RAJPATH CONSTRUCTION. | 4.9 | 0 | 0 | 0
24 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalitala GP from 27.05.21 to 04.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 445/HSD(Camp) | 27/05/2021 | 05/06/2021 | M/S DATTA ENTERPRISE. | 4.62 | 0 | 0 | 0
25 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000443/2021-2022 | 474/HSD(Camp) | 03/06/2021 | 11/06/2021 | S.K.ENTERPRISE. | 4.76 | 0 | 0 | 0
26 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bishpur GP from 01.06.21 to 09.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000436/2021-2022 | 452/HSD(Camp) | 27/05/2021 | 05/06/2021 | TRISHA ENTERPRISE & CO. | 4.67 | 0 | 0 | 0
27 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Jeliakhali GP from 03.06.21 to 13.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000446/2021-2022 | 477/HSD(Camp) | 03/06/2021 | 14/06/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.6 | 0 | 0 | 0
28 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sarberia Agarhati GP from 03.06.21 to 13.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000457/2021-2022 | 488/HSD(Camp) | 03/06/2021 | 14/06/2021 | M/S DATTA ENTERPRISE. | 4.89 | 0 | 0 | 0
29 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-I GP from 27.05.21 to 03.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000402/2021-2022 | 419/HSD(Camp) | 27/05/2021 | 04/06/2021 | M/S DATTA ENTERPRISE. | 4.93 | 0 | 0 | 0
30 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 27.05.21 to 28.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000409/2021-2022 | 425/HSD(Camp) | 27/05/2021 | 29/05/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.87 | 0 | 0 | 0
31 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 27.05.21 to 02.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000428/2021-2022 | 444/HSD(Camp) | 27/05/2021 | 03/06/2021 | MONDAL & CO. (BASIRHAT). | 4.57 | 0 | 0 | 0
32 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 15 & 16 from 02.06.21 to 16.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000438/2021-2022 | 454/HSD(Camp) | 27/05/2021 | 11/06/2021 | M/S RAJPATH CONSTRUCTION. | 4.8 | 0 | 0 | 0
33 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 10.06.21 to 15.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000450/2021-2022 | 481/HSD(Camp) | 03/06/2021 | 09/06/2021 | M/S PROGATI ENTERPRISE. | 4.85 | 0 | 0 | 0
34 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 13.06.21.21 to 16.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000475/2021-2022 | 506/HSD(Camp) | 03/06/2021 | 07/06/2021 | MONDAL & CO. (BASIRHAT). | 4.73 | 0 | 0 | 0
35 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 13.06.21 to 22.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000476/2021-2022 | 507/HSD(Camp) | 03/06/2021 | 13/06/2021 | MONDAL & CO. (BASIRHAT). | 4.55 | 0 | 0 | 0
36 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 16.06.21 to 21.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000493/2021-2022 | 530/HSD(Camp) | 14/06/2021 | 20/06/2021 | M/S DATTA ENTERPRISE. | 4.85 | 0 | 0 | 0
37 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 22.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000494/2021-2022 | 531/HSD(Camp) | 14/06/2021 | 20/06/2021 | M/S PROGATI ENTERPRISE. | 4.85 | 0 | 0 | 0
38 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-I GP from 16.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000500/2021-2022 | 537/HSD(Camp) | 14/06/2021 | 26/06/2021 | M/S DATTA ENTERPRISE. | 4.91 | 0 | 0 | 0
39 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-II GP from 16.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000501/2021-2022 | 538/HSD(Camp) | 14/06/2021 | 26/06/2021 | M/S PROGATI ENTERPRISE. | 4.91 | 0 | 0 | 0
40 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sarberia Agarhati GP from 14.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000503/2021-2022 | 540/HSD(Camp) | 14/06/2021 | 29/06/2021 | M/S PROGATI ENTERPRISE. | 4.89 | 0 | 0 | 0
41 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Disinfection & repairing of tube wells at different places in different GPs within Sandeshkhali-I block due to cyclone 'YAAS' under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000504/2021-2022 | 541/HSD(Camp) | 14/06/2021 | 21/06/2021 | M/S DATTA ENTERPRISE. | 4.95 | 0 | 0 | 0
42 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 16.06.21 to 21.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000505/2021-2022 | 542/HSD(Camp) | 14/06/2021 | 20/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.85 | 0 | 0 | 0
43 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 22.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000506/2021-2022 | 543/HSD(Camp) | 14/06/2021 | 20/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.85 | 0 | 0 | 0
44 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 28.06.21 to 03.07.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000507/2021-2022 | 544/HSD(Camp) | 14/06/2021 | 21/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.68 | 0 | 0 | 0
45 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 19.06.21 to 25.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000508/2021-2022 | 545/HSD(Camp) | 14/06/2021 | 21/06/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.85 | 0 | 0 | 0
46 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 15.06.21 to 20.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000510/2021-2022 | 547/HSD(Camp) | 14/06/2021 | 20/06/2021 | S.K.ENTERPRISE. | 4.76 | 0 | 0 | 0
47 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 21.06.21 to 26.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000511/2021-2022 | 548/HSD(Camp) | 14/06/2021 | 20/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.75 | 0 | 0 | 0
48 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Jeliakhali GP from 14.06.21 to 24.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000518/2021-2022 | 555/HSD(Camp) | 14/06/2021 | 25/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.6 | 0 | 0 | 0
49 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Jeliakhali GP from 25.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000519/2021-2022 | 556/HSD(Camp) | 14/06/2021 | 18/06/2021 | S.K.ENTERPRISE. | 1.67 | 0 | 0 | 0
50 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-I GP from 19.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000520/2021-2022 | 557/HSD(Camp) | 14/06/2021 | 24/06/2021 | M/S NIRMAN CONSTRUCTION. | 3.34 | 0 | 0 | 0
51 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-II GP from 19.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000521/2021-2022 | 558/HSD(Camp) | 14/06/2021 | 24/06/2021 | M/S NIRMAN CONSTRUCTION. | 3.33 | 0 | 0 | 0
52 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Disinfection & repairing of tube wells at different places in different GPs within Sandeshkhali-II block due to cyclone 'YAAS' under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000522/2021-2022 | 559/HSD(Camp) | 14/06/2021 | 21/06/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.96 | 0 | 0 | 0
53 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 1, 2, 3, 4 from 15.06.21 to 26.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000526/2021-2022 | 563/HSD(Camp) | 14/06/2021 | 26/06/2021 | M/S RAJPATH CONSTRUCTION. | 4.6 | 0 | 0 | 0
54 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 17.06.21.21 to 20.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000527/2021-2022 | 564/HSD(Camp) | 14/06/2021 | 18/06/2021 | MONDAL & CO. (BASIRHAT). | 4.73 | 0 | 0 | 0
55 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bishpur GP from 19.06.21 to 27.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000530/2021-2022 | 567/HSD(Camp) | 14/06/2021 | 23/06/2021 | MONDAL & CO. (BASIRHAT). | 4.67 | 0 | 0 | 0
56 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 21.06.21 to 23.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000531/2021-2022 | 568/HSD(Camp) | 14/06/2021 | 17/06/2021 | M/S DATTA ENTERPRISE. | 2.01 | 0 | 0 | 0
57 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 23.06.21 to 30.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000535/2021-2022 | 572/HSD(Camp) | 14/06/2021 | 22/06/2021 | MONDAL & CO. (BASIRHAT). | 3.64 | 0 | 0 | 0
58 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 25.06.21.21 to 28.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000537/2021-2022 | 574/HSD(Camp) | 14/06/2021 | 18/06/2021 | TRISHA ENTERPRISE & CO. | 4.74 | 0 | 0 | 0
59 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Disinfection & repairing of tube wells at different places in different GPs within Hingalganj block due to cyclone 'YAAS' under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000538/2021-2022 | 575/HSD(Camp) | 14/06/2021 | 21/06/2021 | TRISHA ENTERPRISE & CO. | 2 | 0 | 0 | 0
60 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-I GP from 27.05.21 to 04.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000418/2021-2022 | 434/HSD(Camp) | 27/05/2021 | 05/06/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.66 | 0 | 0 | 0
61 | NORTH 24 PARGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm | SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 15 & 16 from 17.06.21 to 30.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000528/2021-2022 | 565/HSD(Camp) | 14/06/2021 | 28/06/2021 | M/S RAJPATH CONSTRUCTION. | 4.48 | 0 | 0 | 0
Total | [13 empty] | 277.36 | 0 | 0