## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-I to III), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001183/2021-2022 | 256/HSD | 07/02/2022 | 17/02/2022 | M/S PROGATI ENTERPRISE. | 3.46 | 0 | 0 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-IV to VI), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001180/2021-2022 | 253/HSD | 07/02/2022 | 17/02/2022 | M/S DATTA ENTERPRISE. | 3.46 | 0 | 0 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Construction of boundary wall at OHR site & CWR site with approach road at CWR site within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001444/2021-2022 | 528/BD | 23/02/2022 | 25/03/2022 | PRITAM MUKHOPADHYAY. | 19.65 | 15.84 | 80.62 | 1
4 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Construction of approach road with cement concrete and other allied works at PH No.- 3 within Hingalganj w/s scheme (Old), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000270/2022-2023 | 1192/HSD | 13/07/2022 | 28/07/2022 | PRASANTA MITRA. | 3.44 | 3.08 | 89.41 | 91
5 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of DI rising main from near Sahapur more to near OHR for damaged portion due to widening & strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000757/2022-2023 | 619/HSD | 07/04/2022 | 22/04/2022 | MONDAL & CO. (BASIRHAT). | 4.81 | 4.67 | 97.13 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of DI rising main from near culvert to near Sahapur more for damaged portion due to widening & strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002879/2021-2022 | 588/HSD | 28/03/2022 | 12/04/2022 | TRISHA ENTERPRISE & CO. | 4.85 | 4.8 | 98.97 | 1
7 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of UPVC pipe line from Hingalganj Kalibari to Hingalganj GP office for damaged portion due to widening & strengthening of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002887/2021-2022 | 596/HSD | 31/03/2022 | 15/04/2022 | TRISHA ENTERPRISE & CO. | 4.18 | 4.18 | 100 | 1
8 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of UPVC pipe line from near Hingalganj GP office to Dakshin Hingalganj at different places (SI office, Garpara, BDO office, Sahapur) for damaged portion within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002891/2021-2022 | 600/HSD | 31/03/2022 | 15/04/2022 | MONDAL & CO. (BASIRHAT). | 4.42 | 4.42 | 100 | 1
9 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia. UPVC pipe line from near Hingalganj Kalibari to near Sahapur more for damaged portion due to widening & Strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002893/2021-2022 | 602/HSD | 31/03/2022 | 15/04/2022 | MONDAL & CO. (BASIRHAT). | 4.26 | 4.26 | 100 | 1
10 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent withdrawing & relaying of different dia. UPVC pipe line at Hingalganj Bazar area, Hingalganj Hospital, BDO Office, Dk. Hingalganj, Garhpara, Sahapur & other places for damaged portion within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002883/2021-2022 | 592/HSD | 29/03/2022 | 13/04/2022 | SARKAR ENTERPRISE | 4.87 | 4.87 | 100 | 1
11 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Protection works for newly laid 200mm dia. UPVC pipe line at N/H/O Susanta Ghosh at Hingalganj within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000915/2022-2023 | 935/HSD | 07/07/2022 | 17/07/2022 | MONDAL & CO. (BASIRHAT). | 2.36 | 2.35 | 99.23 | 1
12 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Laying of 90 mm dia. UPVC pipe line from Boltala Kalupara More to near Katakhali Madrasa within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000917/2022-2023 | 937/HSD | 07/07/2022 | 17/07/2022 | TRISHA ENTERPRISE & CO. | 3.19 | 0 | 0 | 1
13 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000762/2022-2023 | 629/HSD | 08/04/2022 | 23/04/2022 | MONDAL & CO. (BASIRHAT). | 2.45 | 2.45 | 100 | 1
14 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000760/2022-2023 | 622/HSD | 07/04/2022 | 22/04/2022 | M/S NIRMAN CONSTRUCTION. | 2.34 | 0 | 0 | 1
15 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Laying of different dia. UPVC pipe line for damage portion due to construction of concrete road at Mamudpur Purba & Paschim para within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000887/2022-2023 | 936/HSD | 07/06/2022 | 17/06/2022 | MONDAL & CO. (BASIRHAT). | 3.37 | 0 | 0 | 1
16 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia. UPVC pipe line at different places in Hingalganj mouza within Hingalganj W/S/Scheme(Z-I).Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000238/2021-2022 | 1462/BD | 13/08/2021 | 28/08/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 14.98 | 3.49 | 23.27 | 1
17 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at different places in Mamudpur mouza within Hingalganj W/S/Scheme(Z-I). Hingalganj Block under Hasnabad Sub -Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000237/2021-2022 | 1461/BD | 13/08/2021 | 28/08/2021 | M/S K.B.ENTERPRISE. | 16.06 | 14 | 87.15 | 1
18 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in Mamudpur & Hingalganj mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001087/2021-2022 | 142/BD | 18/01/2022 | 18/04/2022 | M/S S.S.ENTERPRISE. (SOUTH) | 390.88 | 350.49 | 89.67 | 1
19 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for for protection works for newly laid different dia. UPVC/DI pipe line at different. places in Mamudpur mouza for Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001137/2021-2022 | 232/BD | 25/01/2022 | 24/02/2022 | MONDAL & CO. (BASIRHAT). | 31.2 | 31.43 | 100.74 | 1
20 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for for protection works for newly laid different dia. UPVC/DI pipe line at different. places in Hingalganj mouza for Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001147/2021-2022 | 235/BD | 25/01/2022 | 09/02/2022 | MONDAL & CO. (BASIRHAT). | 18.36 | 18.36 | 100 | 1
21 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Protection of HDPE rising main pipe line by bamboo piling from near Krishnapada Smriti More to N/H/O Ramesh Gayen for Rejuvenation of Durgapur Baylani w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001924/2021-2022 | 527/HSD | 15/03/2022 | 25/03/2022 | MONDAL & CO. (BASIRHAT). | 4.47 | 0 | 0 | 1
22 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Additional Land development at Head Work Site within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001992/2021-2022 | 1664/HSD | 05/10/2021 | 15/10/2021 | MONDAL & CO. (BASIRHAT). | 4.85 | 4.84 | 99.68 | 1
23 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 160/110 mm dia. HDPE distribution pipe line from near SBI bank to Bankra Bazar due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000423/2022-2023 | 1355/HSD | 03/08/2022 | 18/08/2022 | MONDAL & CO. (BASIRHAT). | 4.74 | 4.74 | 100 | 1
24 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line for damage portion at different places due widening of PWD road of Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000096/2022-2023 | 914/HSD | 07/06/2022 | 22/06/2022 | MONDAL & CO. (BASIRHAT). | 4.9 | 4.9 | 100 | 1
25 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to widening of PWD road from Boltala to Bankra Bazar in connection with retrofitting of Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000431/2022-2023 | 1357/HSD | 03/08/2022 | 18/08/2022 | MONDAL & CO. (BASIRHAT). | 4.64 | 4.64 | 100 | 1
26 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Repairing of Pump House No.-2 within Hingalganj w/s scheme (Old), Hingalgan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000474/2022-2023 | 1399/HSD | 08/08/2022 | 29/08/2022 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 3.46 | 3.46 | 100 | 1
27 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Laying of 90 mm dia. UPVC pipe line from Boltala Kalupara More to near Katakhali Madrasa within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000377/2022-2023 | 937/HSD | 07/06/2022 | 17/06/2022 | TRISHA ENTERPRISE & CO. | 3.19 | 3.19 | 100 | 1
28 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Laying of different dia. UPVC pipe line for damage portion due to construction of concrete road at Mamudpur Purba & Paschim para within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 936/HSD | 07/06/2022 | 17/06/2022 | MONDAL & CO. (BASIRHAT). | 3.37 | 3.37 | 100 | 1
29 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 75 mm dia. HDPE distribution pipe line from PWD road to Hingalganj Police Station, PWD road to Hingalganj BDO office & BDO office to BDO quarter for damage portion in connection with retrofitting of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000394/2022-2023 | 1333/HSD | 02/08/2022 | 17/08/2022 | MONDAL & CO. (BASIRHAT). | 4.83 | 4.83 | 100 | 1
30 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Construction of boundary wall for damaged portion at PH No-2 within Hingalganj w/s scheme (Old), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000477/2022-2023 | 1402/HSD | 08/08/2022 | 29/08/2022 | M/S RAJPATH CONSTRUCTION. | 3.62 | 3.61 | 99.84 | 1
31 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Protection works for newly laid 200mm dia. UPVC pipe line at N/H/O Susanta Ghosh at Hingalganj within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000378/2022-2023 | 935/HSD | 07/06/2022 | 17/06/2022 | MONDAL & CO. (BASIRHAT). | 2.36 | 0 | 0 | 1
32 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. HDPE distribution pipe line from near Electric power house to Bankra Bazar due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000402/2022-2023 | 1340/HSD | 02/08/2022 | 17/08/2022 | MONDAL & CO. (BASIRHAT). | 4.81 | 4.81 | 100 | 1
33 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent resting of 100/150 mm dia DI pipeline by concrete block at different places within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002876/2021-2022 | 584/HSD | 28/03/2022 | 12/04/2022 | TRISHA ENTERPRISE & CO. | 3.09 | 3.06 | 98.98 | 1
34 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia. DI distribution pipe line from near Bankra Bazar to near culvert for damaged portion due to widening & strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002873/2021-2022 | 581/HSD | 28/03/2022 | 12/04/2022 | MONDAL & CO. (BASIRHAT). | 3.74 | 3.67 | 98.18 | 1
35 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Acceptance cum work order for Repairing of Pump House No.-3 & 4, construction of boundary wall & approach road at P.H.No.-3 & other allied works within Hingalganj w/s scheme (Old), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000297/2023-2024 | 2112/BD | 19/07/2023 | 09/08/2023 | GOBINDA DAS. | 9.21 | 9.05 | 98.27 | 46
36 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | REPARING WORKS FOR P.H. NO. 1 & 2 AT TAKI MUNICIPAL W/SS |  |  | ORD/000356/2018-2019 | 1919/HSD | 12/12/2018 |  | M/S RAJPATH CONSTRUCTION. | 2.36 | 4.47 | 189.48 | 0
37 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | SM/09224 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1814/BD | 19/06/2023 |  | Resource Division | 30.8 | 0 | 0 | 0
Total | [13 empty] | 641.01 | 531.29 | 82.88