## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Hingalganj w/s scheme (Zone-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000804/2021-2022 | 1858/HSD. | 17/11/2021 | 02/12/2021 | M/S NIRMAN CONSTRUCTION. | 2.96 | 2.96 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in Bankra mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj Water Supply Scheme (Zone-II), at Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000002/2022-2023 | 1295/ BD | 05/04/2022 | 04/06/2022 | MONDAL PRECISION PVT.LTD | 112.27 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Bermajur w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002571/2021-2022 | 417/HSD | 04/03/2022 | 14/03/2022 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 3.87 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of 150mm dia. DI rising main from near Kathabari more to CWR i/c CWR connection within Hingalganj w/s scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000758/2022-2023 | 620/HSD | 07/04/2022 | 22/04/2022 | M/S NIRMAN CONSTRUCTION. | 3.28 | 3.28 | 99.98 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000863/2022-2023 | 622/HSD | 07/04/2022 | 22/04/2022 | M/S NIRMAN CONSTRUCTION. | 2.34 | 2.34 | 100 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Work Order for " Providing Functional Household Tap Connection (FHTC) in Sandlerbil Mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj W/S/Scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, P.H.E.Dte." | Assistant Engineer | Junior Engineer | ORD/000257/2020-2021 | 49/BD | 13/01/2021 | 13/04/2021 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 155.31 | 29.14 | 18.76 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for for protection works for newly laid different dia. UPVC/DI pipe line at different. places in khosbas, Singherkati mouza & Kanaknagar Mouza for Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001149/2021-2022 | 237/BD | 25/01/2022 | 24/02/2022 | M/S PROGATI ENTERPRISE. | 31.04 | 31.03 | 99.96 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Protection of different dia. UPVC pipe line by UC Bullah pile at different places in Paschim Sandelerbill Uttarpara within Hingalganj W/S/Scheme(Z-II). Hingalganj Block under Hasnabad Sub -Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002069/2021-2022 | 1470/BD. | 13/08/2021 | 28/08/2021 | M/S B.K.ENTERPRISE. | 15.23 | 2.57 | 16.88 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places for Rejuvenation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001666/2021-2022 | 420/HSD | 04/03/2022 | 14/03/2022 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.82 | 0 | 0 | 1
10 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at different places in Sandelerbill mouza within Hingalganj W/S/Scheme(Z-II). Hingalganj Block under Hasnabad Sub -Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/002093/2021-2022 | 1463/BD. | 13/08/2021 | 28/08/2021 | M/S PROGATI ENTERPRISE. | 15.81 | 2.48 | 15.69 | 1
11 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in Bankra mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj Water Supply Scheme (Zone-II), at Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002126/2021-2022 | 1295/BD. | 26/07/2021 | 24/09/2021 | MONDAL PRECISION PVT.LTD | 115.98 | 100.18 | 86.38 | 1
12 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to widening of PWD road from Bankra Bazar to Rupamari more in connection with retrofitting of Hingalganj w/s Scheme (Zone-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000428/2022-2023 | 1356/HSD | 03/08/2022 | 18/08/2022 | M/S NIRMAN CONSTRUCTION. | 2.9 | 2.9 | 100 | 1
13 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 140/110/90/75 mm dia. HDPE distribution pipe line from Bankra Bazar to Rupamari more due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000398/2022-2023 | 1337/HSD | 02/08/2022 | 17/08/2022 | M/S NIRMAN CONSTRUCTION. | 4.29 | 4.29 | 100 | 1
14 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002572/2021-2022 | 406/HSD | 04/03/2022 | 14/03/2022 | S.K.ENTERPRISE. | 3.98 | 3.97 | 99.85 | 1
15 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Bankra Dobar mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002215/2020-2021 | 491/BD. | 26/02/2021 | 28/03/2021 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 3.45 | 3.45 | 100 | 1
16 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Protection works for protection of DI rising main at near PH No- 3 (Old LS) within Hingalganj w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000247/2022-2023 | 1156/HSD | 12/07/2022 | 22/07/2022 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 2.53 | 2.53 | 99.75 | 1
17 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of 160 mm dia. HDPE pipe line from PH No- 4 to near Kathabari more due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002875/2021-2022 | 583/HSD | 28/03/2022 | 12/04/2022 | SARKAR ENTERPRISE | 4.94 | 4.94 | 100 | 1
18 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the different mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000667/2022-2023 | 2922/BD | 26/09/2022 | 26/10/2022 | M/S RAJPATH CONSTRUCTION. | 11.95 | 11.94 | 99.97 | 1
19 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 200/180/160 mm dia. HDPE distribution pipe line from Kathabari more to Rupamari more due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 1341/HSD | 02/08/2022 | 17/08/2022 | M/S NIRMAN CONSTRUCTION. | 4.66 | 4.66 | 100 | 1
20 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line for damage portion at different places due widening of PWD road of Hingalganj w/s Scheme (Zone-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000432/2022-2023 | 1358/HSD | 03/08/2022 | 18/08/2022 | M/S NIRMAN CONSTRUCTION. | 4.9 | 4.9 | 100 | 1
21 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia.UPVC/DI pipe line at different places in Bankra & Bankra Dobar mouza within Hingalganj W/S/Scheme(Z-II). Hingalganj Block under Hasnabad Sub-Division P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/002125/2021-2022 | 1464/BD. | 13/08/2021 | 12/09/2021 | MONDAL & CO. (BASIRHAT). | 31.68 | 5.28 | 16.68 | 1
22 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia. UPVC pipe line at different places in Bankra & Bankra Dobar Mouza due to widening & strengthing of PWD road for damage portion within Hingalganj W/S Scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002885/2021-2022 | 594/HSD | 29/03/2022 | 13/04/2022 | M/S NIRMAN CONSTRUCTION. | 4.49 | 4.49 | 100 | 1
23 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Acceptance cum work order for Construction of boundary wall at OHR site & CWR site (PH No.-3) within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001436/2021-2022 | 527/BD | 23/02/2022 | 25/03/2022 | ABDUL HAMID GAZI. | 22.43 | 20.86 | 92.99 | 1
24 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 941/BD | 28/03/2022 | 28/03/2022 | Resource Division | 150.53 | 0 | 0 | 0
25 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 1438/BD | 23/05/2022 | 23/05/2022 | Resource Division | 9.71 | 0 | 0 | 0
26 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 961/BD | 29/03/2022 | 29/03/2022 | Resource Division | 115.45 | 0 | 0 | 0
27 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | SM/09225 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 1815/BD | 19/06/2023 | 19/06/2023 | Resource Division | 18.48 | 0 | 0 | 0
Total | [13 empty] | 859.29 | 248.21 | 28.89