## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Patua W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | SM/09730 | Retrofitting | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area under Patua Water Supply Scheme at SWARUPNAGAR Block, Dist.- North 24 Parganas under Barasat Division. PHE. Dte. (PHASE-I) | Assistant Engineer | Junior Engineer | ORD/000007/2022-2023 | 1177/BD | 19/04/2022 | 18/07/2022 | KINGS & CO. | 193.55 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Patua W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | SM/09730 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 2342/BD | 26/09/2022 | 26/09/2022 | Resource Division | 24.12 | 0 | 0 | 0
Total | [13 empty] | 217.68 | 0 | 0