## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Land development at tube well site-1 within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001025/2021-2022 | 13/HSD | 04/01/2022 | 19/01/2022 | M/S DATTA ENTERPRISE. | 4.93 | 4.87 | 98.92 | 1
2 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Sinking of 1 No. 360.00 mtr. Deep 100 X 40 mm. dia. trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-2 for Nityabaria w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001041/2021-2022 | 27/HSD | 04/01/2022 | 19/01/2022 | M/S GHOSH CONSTRUCTION. | 3.14 | 2.58 | 82.29 | 1
3 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Sinking of 1 No. 360.00 mtr. Deep 100 X 40 mm. dia. trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Nityabaria w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001039/2021-2022 | 25/HSD | 04/01/2022 | 19/01/2022 | GOBINDA DAS. | 3.14 | 2.7 | 85.9 | 1
4 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Land development at tube well site-2 within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001027/2021-2022 | 15/HSD | 04/01/2022 | 14/01/2022 | M/S PROGATI ENTERPRISE. | 1.59 | 1.59 | 99.91 | 1
5 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Additional land development for connecting road at tube well site-1 (H/W site) within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000113/2022-2023 | 930/HSD | 07/06/2022 | 28/06/2022 | M/S DATTA ENTERPRISE. | 2.01 | 2.01 | 100 | 1
6 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Additional land development at tube well site-1 (H/W site) within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000114/2022-2023 | 931/HSD | 07/06/2022 | 28/06/2022 | M/S PROGATI ENTERPRISE. | 4.53 | 4.53 | 100 | 1
7 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance Cum Work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2022-2023 | 2245/BD | 28/07/2022 | 27/08/2022 | M/S K.P.PAL. | 54.44 | 36.84 | 67.67 | 0
8 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Geotechnical investigation for the construction of proposed OHR (Capacity 400 M3 ) at HW site within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000550/2022-2023 | 1380/HSD | 04/08/2022 | 03/09/2022 | RANJIT MITRA SUPPLIERS | 0.73 | 0.73 | 100 | 0
9 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) within Nityabaria w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000209/2022-2023 | 1889/BD | 05/07/2022 | 03/09/2022 | BABUSONA CONSTRUCTION. | 12.5 | 12.63 | 101.03 | 10
10 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Protection work for protection of 2nd pump house at canal side by UC bullah pilling within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte | Assistant Engineer |  | ORD/000860/2023-2024 | 1046/HSD | 31/08/2023 | 10/09/2023 | BABUSONA CONSTRUCTION. | 0.95 | 0.95 | 99.87 | 100
11 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for Additional height for construction of PH No- 2 & other allied works at located canal side within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/001289/2023-2024 | 1411/HSD | 06/11/2023 | 16/11/2023 | BABUSONA CONSTRUCTION. | 0.97 | 0.97 | 100 | 100
12 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Deposit Works, other than new service connection (GL:4704001) under AE-I Nityaberia |  |  | BILL/01867/2023-2024 | BP-99-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.94 | 0 | 0 | 0
13 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | New Service Connection under AE-I Nityaberia |  |  | BILL/01864/2023-2024 | BP-98-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.91 | 0 | 0 | 0
14 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Deposit works, Other Than new Service Connection under AE-I Nityaberia |  |  | BILL/01865/2023-2024 | BP-97-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.95 | 0 | 0 | 0
15 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | New Service Connection under AE-I Nityaberia |  |  | BILL/01866/2023-2024 | BP-100-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.85 | 0 | 0 | 0
16 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (New) under Nityaberia W/S Scheme District of 24 Pgs. (N) NIET No.- 27 of EE/EMD of 2022-23 (Sl. No.- 29) | Assistant Engineer | Junior Engineer | ORD/000001/2023-2024 | 1438/EMD | 10/04/2023 | 10/05/2023 | M/S DAS ENTERPRISE | 26.77 | 24.18 | 90.29 | 90
17 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Outdoor illumination by supplying and installing of 15 Watt Solar Street Light at P.H No.I under Nityaberia W/S Scheme, Sandeshkhali-II Block, Dist. 24 pgs (N) under Eastern Mechanical Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000438/2024-2025 | 1199/EMSD-I | 27/09/2024 | 27/10/2024 | RMD TRADING | 1.42 | 0 | 0 | 0
18 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 3478/BD | 10/12/2024 | 10/12/2024 | Resource Division | 34.89 | 0 | 0 | 0
19 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Formal work order for "Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection & Construction of 400 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Department design, drawing & specification including bored pile & pile cap in connection with Nityaberia water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000721/2023-2024 | 2577/BD | 25/08/2023 | 25/08/2026 | KINGS & CO. | 859.85 | 173.69 | 20.2 | 25
20 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 for Nityaberia water supply scheme, Sandeskhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001532/2024-2025 | 387/HSD | 10/02/2025 | 20/02/2025 | KINGS & CO. | 0.95 | 0 | 0 | 0
21 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME | SM/10182 | New | Formal work order for Additional Laying of UPVC distribution pipe line and other allied works within Nityaberia water supply scheme Sandeshkhali-I Block and Surface Water Based Piped Water Supply Scheme for Hasnabad, under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001020/2024-2025 | 3745/BD | 27/12/2024 | 22/12/2025 | KINGS & CO. | 163.99 | 0 | 0 | 25
Total | [13 empty] | 1198.45 | 268.27 | 22.38