## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Kurulia (Zone-I) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002784/2021-2022 | 138/BON | 18/02/2022 | 05/03/2022 | UMWELT ENGINEER PVT.LTD. | 4.05 | 4.03 | 99.56 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I(Z-I) under Kurulia W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 05) |  |  | ORD/000115/2022-2023 | 6142/EMD | 11/11/2022 | 11/12/2022 | SWAPAN ENTERPRISE | 12.83 | 11.66 | 90.85 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II(Z-I) under Kurulia W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.-06) |  |  | ORD/000116/2022-2023 | 6143/EMD | 11/11/2022 | 11/12/2022 | PADMA ENGINEERING CO. | 12.76 | 11.88 | 93.05 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KURULIA (Zone-II) Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/002293/2020-2021 | 490/BD. | 26/02/2021 | 12/04/2021 | ORIENT CONSTRUCTION. | 67.42 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Kurulia (Zone-I) water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000817/2022-2023 | 3589/BD | 08/12/2022 | 23/12/2022 | M/S SUKANTA ENTERPRISE. | 15.04 | 14.07 | 93.59 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Renovation and repairing of Boundary wall at 2nd T/W site for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000642/2023-2024 | 612/Bon | 08/08/2023 | 29/08/2023 | ROY CHOWDHURY CONSTRUCTION. | 2.76 | 2.72 | 98.55 | 100
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Supply, delivery and fitting fixing of change over switch, cable etc. at pump house no. I (Z-I), under Kurulia W/S Scheme in connection with FHTC. | Assistant Engineer | Junior Engineer | ORD/001185/2023-2024 | 1774/EMSD-I | 10/08/2023 | 20/08/2023 | SWAPAN ENTERPRISE | 1.23 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000637/2023-2024 | 620/Bon | 08/08/2023 | 23/08/2023 | ONKAR ENTERPRISE. | 2.4 | 2.35 | 97.73 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 1366/BD | 13/05/2022 | 13/05/2022 | Resource Division | 8.83 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 1671/BD | 13/06/2022 | 13/06/2022 | Resource Division | 8.71 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Kurulia (Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000777/2022-2023 | 1243/BD | 26/04/2022 | 25/07/2022 | M/S NANDY ENTERPRISE | 470.6 | 317.22 | 67.41 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | SM/10298 | Augmentation | Construction of Latrine at Head Work site and Renovation of PH No - 1 & 2 and allied works for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000612/2025-2026 | 662/Bon | 23/05/2025 | 07/07/2025 | M/S SAYAN ENTERPRISE. | 3.51 | 0 | 0 | 0
Total | [13 empty] | 610.14 | 363.92 | 59.65