## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under panchita W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001890/2022-2023 | 6145 / EMD | 14/08/2022 | 13/09/2022 | P.K. ENTERPRISE | 12.82 | 10.38 | 80.96 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Acceptance cum work order for Repair and renovation works of 180 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir alongwith rising main connection with 2nd Tube well for Augmentation of Panchita Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000452/2024-2025 | 3038/BD | 22/10/2024 | 06/12/2024 | DEBAPRASAD MONDAL. | 15.61 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Panchita W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (PART-B). | Assistant Engineer |  | ORD/000088/2024-2025 | 1769/BD | 01/07/2024 | 16/07/2024 | A.D.ENTERPRISE. | 24.28 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Panchita W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (PART-A). | Assistant Engineer | Junior Engineer | ORD/000083/2024-2025 | 1768/BD | 01/07/2024 | 16/07/2024 | PRABIR KUMAR MONDAL. | 12.13 | 0 | 0 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Panchita Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000009/2022-2023 | 1209/BD | 21/04/2022 | 20/07/2022 | UMWELT ENGINEER PVT.LTD. | 393.47 | 386.33 | 98.19 | 0
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Panchita W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/000119/2022-2023 | 6146/EMD | 11/11/2022 | 11/12/2022 | S.M. ELECTRICALS | 12.81 | 10.88 | 84.94 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Panchita water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000819/2022-2023 | 3591/BD | 08/12/2022 | 23/12/2022 | SAHA CONSTRUCTION & CO | 15.12 | 13.73 | 90.85 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Renovation and repairing of Boundary wall at 2nd T/W site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000569/2023-2024 | 615/Bon | 08/08/2023 | 29/08/2023 | PRABIR KUMAR MONDAL. | 4.15 | 4.11 | 99.1 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000634/2023-2024 | 617/Bon | 08/08/2023 | 25/08/2023 | KAMAL HALDER. | 2.94 | 2.93 | 99.71 | 100
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Acceptance cum work order for Repair & renovation of Pump House at 2nd T/W site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000676/2023-2024 | 604/Bon | 04/08/2023 | 25/08/2023 | PRABIR KUMAR MONDAL. | 1.78 | 0 | 0 | 100
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Urgently repairing and laying of badly damaged pipe line and FHTC connection due to construction of Gram Panchayat surface drain at Nakful area of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000897/2023-2024 | 625/Bon | 08/08/2023 | 23/08/2023 | PRABIR KUMAR MONDAL. | 0.71 | 0.35 | 49.63 | 100
12 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Construction of Approach Road at 2ndT/W site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000971/2023-2024 | 559/Bon | 18/07/2023 | 02/08/2023 | PRABIR KUMAR MONDAL. | 0.87 | 0 | 0 | 100
13 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Panchita Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001740/2023-2024 | 536/BD | 21/02/2024 | 06/04/2024 | PRABIR KUMAR MONDAL. | 14.25 | 0 | 0 | 100
14 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Health assessment of existing OHR of Panchita PWSS (180 cum) and ancillary structures, Bongaon Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2024-2025 | 691/Bon | 07/06/2024 | 22/06/2024 | SIRCON ENGINEERING SERVICES | 3.53 | 0 | 0 | 100
15 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1367/BD | 13/05/2022 |  | Resource Division | 19.79 | 0 | 0 | 0
16 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | SM/10300 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 1672/BD | 13/06/2022 |  | Resource Division | 19.79 | 0 | 0 | 0
Total | [13 empty] | 554.04 | 428.72 | 77.38