## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Kurulia (Zone-I&II) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002909/2021-2022 | 593/Bon | 22/12/2021 | 12/01/2022 | PRABIR KUMAR MONDAL. | 2.52 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Formal work order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of Kurulia(Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (Augmentation). | Assistant Engineer | Junior Engineer | ORD/002038/2021-2022 | 988/BD | 31/03/2022 | 29/06/2022 | H.I.ENTERPRISE. | 360.51 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Making Suitable Foundation at out side of the PUmp House of 1000ltr at PH-I Z-II under Kurulia W/S Scheme, W/O-1037/SD-I, T.No.1131/SD-I |  |  | ORD/000321/2021-2022 | 1037/EMSD-I | 04/05/2021 | 03/06/2021 | TAMAL ENTERPRISE | 0.64 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Making Suitable Foundation at out side of the PUmp House of 1000ltr PV Tank at PH-I Z-II under Kurulia W/S Scheme, W/O-1034/SD-I, T.No.1135/SD-I |  |  | ORD/000323/2021-2022 | 1034/ SD-I | 04/05/2021 | 03/06/2021 | TAMAL ENTERPRISE | 0.69 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Kurulia (Zone-II) water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000818/2022-2023 | 3590/BD | 08/12/2022 | 23/12/2022 | M/S SUKANTA ENTERPRISE. | 15.04 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 1365/BD | 13/05/2022 | 13/05/2022 | Resource Division | 18.73 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 1673/BD | 13/06/2022 | 13/06/2022 | Resource Division | 17.77 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Dobila W/S Scheme, Nabatkati W/S Scheme and Kurulia (Zone-II) W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001163/2023-2024 | 4813/EMD | 09/08/2023 | 08/09/2023 | DEBJYOTI BASU | 78.24 | 0 | 0 | 66
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Repairing and renovation of Boundary wall, Pump House and construction of Approach Road at 2nd Tube Well site for Augmentation of Kurulia (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001055/2024-2025 | 1081/Bon | 02/09/2024 | 17/09/2024 | M/S SAYAN ENTERPRISE. | 4.38 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Kurulia (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001239/2023-2024 | 789/Bon | 10/10/2023 | 25/10/2023 | A.D.ENTERPRISE. | 1.59 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Kurulia (Zone-I & II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001729/2023-2024 | 521/BD | 20/02/2024 | 21/03/2024 | PRABIR KUMAR MONDAL. | 13.94 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Health assessment of existing OHR of Kurulia (Zone-I) PWSS (225 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000015/2024-2025 | 688/Bon | 07/06/2024 | 22/06/2024 | SIRCON ENGINEERING SERVICES | 4.05 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Health assessment of existing OHR of Kurulia (Zone-II) PWSS (225 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2024-2025 | 689/Bon | 07/06/2024 | 22/06/2024 | SIRCON ENGINEERING SERVICES | 4.53 | 0 | 0 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and tube well connection under Augmentation work at Kurulia W/S Scheme (Zone - II) Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000644/2024-2025 | 3170/BD | 18/11/2024 | 18/12/2024 | MA CONSTRUCTION. | 59.19 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Acceptance cum work order for Hire and labour charges for staging and scaffolding, bamboo baricading and removal of rubbish for dismantling of existing OHR at Head work Site of Kurulia Zone-II Water Supply Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. | Assistant Engineer |  | ORD/001601/2024-2025 | 706/BD | 06/03/2025 | 05/05/2025 | HAQUE ENTERPRISE | 8.76 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | SM/10301 | Augmentation | Construction of Latrine at Head Work site for Augmentation of Kurulia (Zone II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000615/2025-2026 | 670/Bon | 26/05/2025 | 10/07/2025 | SAMBHU RAY CHOWDHURY. | 1.76 | 0 | 0 | 0
Total | [13 empty] | 592.35 | 0 | 0