## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Formal Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household and laying of UPVC Dedicated Main Pipe Line towards different mouza for better supply of drinking water along with pipe protection and Road Restoration work under Augmentation work at Krishnachandrapur W/S Scheme at Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002022/2023-2024 | 887/BD | 14/03/2024 | 12/06/2024 | SAHA CONSTRUCTION & CO | 108.9 | 0 | 0 | 75
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Krishnachandrapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation) | Assistant Engineer | Junior Engineer | ORD/000008/2022-2023 | 1174/BD | 19/04/2022 | 18/07/2022 | SUPRITI ENTERPRISE. | 392.59 | 260.82 | 66.43 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Krishnachandrapur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002952/2021-2022 | 636/BON | 31/12/2021 | 21/01/2022 | ACHINTA KUMAR HALDER. | 1.26 | 1.14 | 90.94 | 1
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Acceptance cum work order for Repair and renovation works of R.C.C. Elevated Reservoir of 456 cum for Krishnachandrapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/001013/2022-2023 | 189/BD | 20/01/2023 | 19/02/2023 | TRISHA ENTERPRISE & CO. | 19.03 | 18.97 | 99.71 | 100
5 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Krishnachandrapur W/S Scheme and Chowberia W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001173/2023-2024 | 4801/EMD | 09/08/2023 | 01/01/2025 | A.G ENTERPRISE. | 52.15 | 0 | 0 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Krishnacandrapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000640/2023-2024 | 623/Bon | 08/08/2023 | 02/09/2023 | ROY CHOWDHURY CONSTRUCTION. | 4.73 | 2.36 | 49.91 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Krishnachandrapur Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001154/2023-2024 | 2945/BD | 27/09/2023 | 26/11/2023 | JOY GURU ENTERPRISE | 32.24 | 0 | 0 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Krishnachandrapur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001739/2023-2024 | 535/BD | 21/02/2024 | 06/04/2024 | ANKUSH CONSTRUCTION & CO. | 17.78 | 0 | 0 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1362/BD | 13/05/2022 |  | Resource Division | 20.47 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | SM/10308 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 1674/BD | 13/06/2022 |  | Resource Division | 20.09 | 0 | 0 | 0
Total | [13 empty] | 669.23 | 283.29 | 42.33