## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Gangrapota water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002958/2021-2022 | 536/BON | 03/11/2021 | 24/11/2021 | GHOSH CONSTRUCTION. | 2.52 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Repairing & Renovation of 01No. Pump House (PH-III) and allied works at Gangrapota water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002968/2021-2022 | 635/ BON | 31/12/2021 | 15/01/2022 | GHOSH CONSTRUCTION. | 1.26 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Making Suitable Foundation at out side of the PUmp House of 1000ltr PV Tank at PH-I Z-II under Kurulia W/S Scheme, W/O-1036/SD-I, T.No.1132/SD-I |  |  | ORD/000324/2021-2022 | 1036/SD I | 04/05/2021 | 03/06/2021 | TAMAL ENTERPRISE | 0.63 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Gangrapota water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000827/2022-2023 | 3621/BD | 12/12/2022 | 27/12/2022 | DHELA BABA ENTERPRISE | 15.12 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Ganrapota W/S Scheme District of 24 Pgs. (N) (Block- Baduria).NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.-04) |  |  | ORD/001893/2022-2023 | 6141 / EMD | 14/08/2022 | 13/09/2022 | TRIDENT ENTERPRISE | 9.29 | 0 | 0 | 1
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under gangrapota W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001908/2022-2023 | 6140 / EMD | 14/08/2022 | 13/09/2022 | GHOSH AND GHOSH | 12.82 | 0 | 0 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Gangrapota Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation) | Assistant Engineer | Junior Engineer | ORD/000004/2022-2023 | 1004/BD | 04/04/2022 | 03/07/2022 | M/S DIPAK ENTERPRISE | 298.46 | 0 | 0 | 1
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Ganrapota W/S Scheme District of 24 Pgs. (N) (Block- Baduria).NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.-04) |  |  | ORD/002485/2022-2023 | 6141-EMD | 11/11/2022 | 11/04/2023 | TRIDENT ENTERPRISE | 2.7 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1369/BD | 13/05/2022 | 13/05/2022 | Resource Division | 26.76 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1675/BD | 13/06/2022 | 13/06/2022 | Resource Division | 76.64 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gangrapota Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001170/2023-2024 | 2928/BD | 26/09/2023 | 26/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Construction of Approach Road at 2nd Pump House site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000967/2023-2024 | 555/Bon | 18/07/2023 | 02/08/2023 | M/S SAYAN ENTERPRISE. | 0.8 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Gangrapota Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001759/2023-2024 | 519/BD | 20/02/2024 | 21/03/2024 | S.D. CONSTRUCTION. | 15.09 | 0 | 0 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Acceptance cum work order for Renovation and repairing of Balance Part of Boundary wall at OHR site for Augmentation of Gangrapota Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001439/2024-2025 | 444/BD | 10/02/2025 | 12/03/2025 | M.M.B. ENTERPRISE | 13.5 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household of Chanda, Gangrapota, Gobrapur and Kamalapur mouzas including laying of UPVC pipe with pile work under Augmentation work at Gangrapota W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000020/2025-2026 | 1387/BD | 30/04/2025 | 29/07/2025 | ONKAR ENTERPRISE. | 76.95 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Special repairing work in connection with Augmentation Work at Gangrapota W/S Scheme under Bongaon Block within the jurisdiction of Bongaon Sub-Division under, Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/003114/2024-2025 | 376/Bon | 13/03/2025 | 28/03/2025 | VAI ENTERPRISE. | 0.57 | 0 | 0 | 100
Total | [13 empty] | 569.22 | 0 | 0