## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Gangrapota water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000827/2022-2023 | 3621/BD | 12/12/2022 | 27/12/2022 | DHELA BABA ENTERPRISE | 15.12 | 13.34 | 88.23 | 0
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Ganrapota W/S Scheme District of 24 Pgs. (N) (Block- Baduria).NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.-04) |  |  | ORD/001893/2022-2023 | 6141 / EMD | 14/08/2022 | 13/09/2022 | TRIDENT ENTERPRISE | 9.29 | 9.29 | 100 | 1
3 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under gangrapota W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001908/2022-2023 | 6140 / EMD | 14/08/2022 | 13/09/2022 | GHOSH AND GHOSH | 12.82 | 10.58 | 82.56 | 1
4 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Ganrapota W/S Scheme District of 24 Pgs. (N) (Block- Baduria).NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.-04) |  |  | ORD/002485/2022-2023 | 6141-EMD | 11/11/2022 | 10/04/2023 | TRIDENT ENTERPRISE | 2.7 | 2.7 | 100 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Gangrapota Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation) | Assistant Engineer | Junior Engineer | ORD/000004/2022-2023 | 1004/BD | 04/04/2022 | 03/07/2022 | M/S DIPAK ENTERPRISE | 298.46 | 282.74 | 94.73 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Gangrapota water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002958/2021-2022 | 536/BON | 03/11/2021 | 24/11/2021 | GHOSH CONSTRUCTION. | 2.52 | 2.48 | 98.38 | 1
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Repairing & Renovation of 01No. Pump House (PH-III) and allied works at Gangrapota water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002968/2021-2022 | 635/ BON | 31/12/2021 | 15/01/2022 | GHOSH CONSTRUCTION. | 1.26 | 1.15 | 90.94 | 1
8 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Making Suitable Foundation at out side of the PUmp House of 1000ltr PV Tank at PH-I Z-II under Kurulia W/S Scheme, W/O-1036/SD-I, T.No.1132/SD-I |  |  | ORD/000324/2021-2022 | 1036/SD I | 04/05/2021 | 03/06/2021 | TAMAL ENTERPRISE | 0.63 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gangrapota Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001170/2023-2024 | 2928/BD | 26/09/2023 | 26/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 0 | 0 | 100
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Construction of Approach Road at 2nd Pump House site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000967/2023-2024 | 555/Bon | 18/07/2023 | 02/08/2023 | M/S SAYAN ENTERPRISE. | 0.8 | 0 | 0 | 100
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Gangrapota Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001759/2023-2024 | 519/BD | 20/02/2024 | 21/03/2024 | S.D. CONSTRUCTION. | 15.09 | 0 | 0 | 100
12 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1369/BD | 13/05/2022 |  | Resource Division | 26.76 | 0 | 0 | 0
13 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | SM/10309 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1675/BD | 13/06/2022 |  | Resource Division | 76.64 | 0 | 0 | 0
Total | [13 empty] | 478.2 | 322.27 | 67.39