## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Bagdah Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000001/2022-2023 | 1002/BD | 04/04/2022 | 03/07/2022 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 450.95 | 259.19 | 57.48 | 80
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under Bagdah W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001903/2022-2023 | 6138 / EMD | 21/03/2023 | 20/04/2023 | M/S.A.K. BANERJEE. | 12.85 | 10.38 | 80.79 | 1
3 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Bagda W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No. 15 of EE/EMD of 2022-23 (Sl. No.- 02) |  |  | ORD/002034/2022-2023 | 6139/ EMD | 14/08/2022 | 13/09/2022 | GOENKA ENTERPRISE | 12.87 | 8 | 62.14 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Construction and Repairing works of damaged part of Boundary wall, Main Gate, Drain, Valve Chamber and allied works due to DI Pipe stacking and shifting at Bagdah High School play ground for Bongaon-Bagdah surface water based PWSS within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000886/2024-2025 | 1393/Bon | 27/11/2024 | 22/12/2024 | VAI ENTERPRISE. | 4.73 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Making suitable foundation at the out side of the pump house for installation of 1000Lt PVC tank for feeding chlorine solution by automatic chlorinator & other works at Ph I under Bagdah w/s scheme 24 Pgs(N) |  |  | ORD/000495/2021-2022 | 1035/EMSD I | 04/05/2021 | 21/05/2021 | TALUKDER & CO. | 0.92 | 0.92 | 100 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Bagdah Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000641/2023-2024 | 624/Bon | 08/08/2023 | 23/08/2023 | TAPAN GHOSH. | 2.39 | 2.38 | 99.28 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Bagdah Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001153/2023-2024 | 2927/BD | 26/09/2023 | 26/10/2023 | DHELA BABA ENTERPRISE | 16.1 | 0 | 0 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Health assessment of existing OHR of Bagdah PWSS (341 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000014/2024-2025 | 687/Bon | 07/06/2024 | 22/06/2024 | SIRCON ENGINEERING SERVICES | 4.74 | 0 | 0 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 1361/BD | 13/05/2022 |  | Resource Division | 23.36 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | SM/10310 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 1670/BD | 13/06/2022 |  | Resource Division | 21.96 | 0 | 0 | 0
Total | [13 empty] | 550.87 | 280.86 | 50.98