## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance Cum Work Order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2023-2024 | 1096/BD | 06/04/2023 | 06/05/2023 | MONDAL & CO. (BASIRHAT). | 62.05 | 47.57 | 76.66 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Dk Durgamandop FP School, DTD Sahid Smriti Bidyalaya & Durgamandop Sardar para High School within the command area of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000867/2023-2024 | 1053/HSD | 31/08/2023 | 07/09/2023 | M/S RAJPATH CONSTRUCTION. | 0.69 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Durgamandop water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 2401/BD | 17/08/2022 | 15/11/2022 | MONDAL & CO. (BASIRHAT). | 287.51 | 266.78 | 92.79 | 1
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Durga-Mandap W/S Scheme District of North 24 Pgs. Tender No.- 08 (Sl. No.-02) of EE/EMD of 2022-23 |  |  | ORD/002404/2022-2023 | 3383 /EMD | 14/08/2022 | 13/09/2022 | C.M.S. ENGINEERING CONCERN. | 11.34 | 10.36 | 91.34 | 45
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000858/2023-2024 | 1044/HSD | 31/08/2023 | 10/09/2023 | ANKUSH CONSTRUCTION & CO. | 0.93 | 0.93 | 100 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000857/2023-2024 | 1043/HSD | 31/08/2023 | 10/09/2023 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000843/2023-2024 | 2652/BD | 01/09/2023 | 01/10/2023 | MONDAL & CO. (BASIRHAT). | 56.83 | 56.73 | 99.82 | 84
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/001293/2023-2024 | 1415/HSD | 06/11/2023 | 13/11/2023 | SARKAR ENTERPRISE | 0.83 | 0.83 | 100 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 2471/BD | 24/08/2022 | 24/08/2022 | Resource Division | 7.56 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Durga-Mandap W/S Scheme District of North 24 Pgs. Tender No.- 08 (Sl. No.-01) of EE/EMD of 2022-23 |  |  | ORD/003002/2022-2023 | 3382EMD | 09/09/2022 | 09/10/2022 | BOSE & CHATTERJEE INDUSTRIES | 11.36 | 10.35 | 91.07 | 70
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Durgamandop water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001852/2023-2024 | 276/HSD | 06/03/2024 | 16/03/2024 | ANKUSH CONSTRUCTION & CO. | 0.97 | 0.97 | 99.95 | 83
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Durgamandop Mouza within Durgamandop w/s scheme , Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 888/HSD | 07/08/2024 | 17/08/2024 | SARKAR ENTERPRISE & CO. | 0.94 | 0.93 | 98.87 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Durgamandop water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001252/2023-2024 | 4182/BD | 30/10/2023 | 31/10/2025 | DEBASIS SAMADDAR | 150.76 | 83.99 | 55.71 | 60
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection for augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001440/2024-2025 | 110/BD | 09/01/2025 | 25/03/2025 | MD.SALIM GAZI. | 11.68 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000067/2025-2026 | 1753/BD | 28/05/2025 | 27/07/2025 | MONDAL & CO. (BASIRHAT). | 251.97 | 0 | 0 | 0
Total | [13 empty] | 856.33 | 480.35 | 56.09